## AUG-21 (hidden)
Tentative Planned Outages for the month of August-2021 of Hospet Urban
Name of Division | Name of Subdivision | Name of SubStation | Name of Feeder | Feeder Code | Feeder Type | Date | Outage From | Outage To | Duration Of Outage | Outage Type | Area Affected | Reason of Outage
Hosapete Urban | USD-1 | 33KV MUSS, HOSAPETE | F-5 AMARAVATHI FEEDER | 40020575589 | URBAN | 2021-08-11 | 10:00:00AM | 01:00:00PM | 3.00 HRS | SCHELDULED | Industrial area, Rajeev Nagar, Chittawadigi, Amaravathi, Sai Ram Badavane, Kalyan Nagar, Mallinath Layout | Jungle cutting & line GOS maintainance
| USD-1 | 33KV MUSS, HOSAPETE | F-4 Ennoble | 40020575583 | URBAN | 2021-08-12 | 10:00:00AM | 01:00:00PM | 3.00 HRS | SCHELDULED | Indira Nagar, Rayal orchid Hotel | Line GOS Maintainance
| USD-2 | 110KV MUSS SANKALAPURA | F8-MP.PRAKASH NAGAR | 40020575601 | URBAN | 10.08.2021 | 10:00:00AM | 01:00:00PM | 3.00 HRS | SCHELDULED | MP.PRAKASH NAGAR, SANKALAPURA, A.S.GUDI, SAI COLONY, KN.HALLI | GOS MAINTENANCE
| RSD | 110/11KV MUSS Sanklapura | BV Gere | F7 | IP | 14.08.2021 | 09:00:00AM | 01:00:00PM | 4Hours | SCHELDULED | Kakubalu, GV Gere, Pk Halli & Vaddarahalli | Jungle Cutting
| RSD | 110/11KV MUSS Sanklapura | Rajapura | F13 | NJY | 16.08.2021 | 11:00:00AM | 01:00:00PM | 2 Hours | SCHELDULED | Kakubalu, GV Gere, Kallahalli & Rajapura | DTC Mantainance
| RSD | 110/11KV MUSS Sanklapura | Basavanadurga | F5 | NJY | 18.08.2021 | 10:00:00AM | 12:00:00PM | 2 Hours | SCHELDULED | Nagenahalli, Hosuru, Basavanadurga, Benakapura | 11KV GOS Mantanance
| RSD | 110/11KV MUSS Kamalapura | P.K.Halli | F7 | IP | 20.08.2021 | 09:00:00AM | 12:00:00PM | 3 Hours | SCHELDULED | PK Halli, Vadrahalli, BV Gere | Stringing of 11KV Loose Spans
| RSD | 110/11KV MUSS Kamalapura | Hostel | F13 | NJY | 22.08.2021 | 09:00:00AM | 12:00:00PM | 3 Hours | SCHELDULED | PK Halli, Vadrahalli, BV Gere , Gadiganuru, Dharmasagara & Bhuvanahalli | Replacement of Damaged Poles
| RSD | 66/11KV Venkatapura | M.M.Halli | F1 | Urban | 18.08.2021 | 11:00:00AM | 06:00:00PM | 7 Hours | SCHELDULED | M.M.Halli Town & Nandibandi Pumpset | Jungle Cutting & Insulater Manatanance
| RSD | 66/11KV Venkatapura | Thimmalapura | F9 | NJY | 20.08.2021 | 12:00:00AM | 02:00:00PM | 2 Hours | SCHELDULED | Garaga, Nagalapura, Pothalakatte & TB Thanda ETC | Stringing of 11KV Loose Spans
| RSD | 66/11KV Venkatapura | Galemmagudi | F2 | NJY | 22.08.2021 | 11:00:00AM | 01:00:00PM | 2 Hours | SCHELDULED | Hanumanahalli, Galemmagudi Danapura | GOS Mantanance & Jungle Cutting
| RSD | 66/11KV Venkatapura | Nagalapura | F8 | IP | 24.08.2021 | 07:00:00AM | 10:00:00PM | 3 Houurs | SCHELDULED | Gunda, Byalakundi, DN Kere & Gollarahalli | Jungle Cutting
| RSD | 66/11KV Venkatapura | Chilakanahatti | F6 | IP | 26.08.2021 | 10:00:00PM | 02:00:00PM | 4 Houurs | SCHELDULED | Haruvanahalli, Chilakanahatti, Thimmalapura & TB Thanda | Jungle Cutting & replacement of Pin Insulater
| RSD | 110/11KV MUSS Kampli | Kampli Town | F2 | Urban | 14.08.2021 | 11:00:00PM | 01:00:00PM | 2 Hours | SCHELDULED | Main Bazar, Basavanna Temple, Housing Board Colony, Sn Pet Are | Mantanance Work
| RSD | 110/11KV MUSS Kampli | Kampli Kottal | F4 | Urban | 16.08.2021 | 10:30:00PM | 12:30:00PM | 1 Hour | SCHELDULED | Vinayaka Nagara, Idira Nagara, Sanapura Road, Kottal Road | DTC Wiring
| RSD | 110/11KV MUSS Kampli | Industrial | F3 | Urban | 18.08.2021 | 10:00:00AM | 11:00:00AM | 1 Hour | SCHELDULED | Kottal | GOS Mantanance
| RSD | 110/11KV MUSS Kampli | Basaveshwara Nagara | F12 | Urban | 19.08.2021 | 11:30:00AM | 12:30:00PM | 1 Hour | SCHELDULED | Basaveshwara Nagara, Maruthi Nagara | Line Mantanance
| RSD | 110/11KV MUSS Kampli | Prabhu Camp | F13 | Urban | 20.08.2021 | 10:00:00AM | 1:00:00PM | 3Hours | SCHELDULED | Sugar Factory, Prabhu Camp, Huligemma Camp | Line Mantanance
| RSD | 110/11KV MUSS Kamalapura | Kamalapura Town | F12 | Urban | 14.08.2021 | 9:00:00AM | 11:00:00AM | 2 Hours | SCHELDULED | Kamalapura Town | Jungle Cutting
| RSD | 110/11KV MUSS Kamalapura | Nallapura | F3 | NJY | 16.08.2021 | 10:00:00PM | 01:00:00PM | 3 Houurs | SCHELDULED | Nallapura, Hosa Chinnapura SR Thanda | GOS Mantanance
| RSD | 110/11KV MUSS Kamalapura | Malapanagudi | F2 | Rural | 18.08.2021 | 10:00:00PM | 01:00:00PM | 3 Houurs | SCHELDULED | Hosa Malapanagudi, galemmagudi | Stringing of 11KV Loose Spans
| RSD | 110/11KV MUSS Kamalapura | University | F4 | Rural | 20.08.2021 | 11:00:00AM | 01:00:00PM | 2 Hours | SCHELDULED | University, Nallapura | GOS Mantanance & Jungle Cutting
| RSD | 110/11KV MUSS Kampli | Vidyapeeta | F6 | NJY | 9.08.2021 | 11:00:00AM | 01:00:00PM | 2 Hours | SCHELDULED | Ramasagara, Kanavi Thimmalapura | Jungle Cuuting
| RSD | 110/11KV MUSS Kampli | KT Pura | F8 | IP | 12.08.2021 | 09:00:00AM | 11:00:00AM | 2 Hours | SCHELDULED | KT Pura Gouramma kere | Jungle Cuuting
| RSD | 110/11KV MUSS Kampli | Belagodhal | F3 | IP | 19.08.2021 | 10:00:00AM | 12:00:00PM | 2 Hours | SCHELDULED | Belagodhal | Jungle Cuuting

## Sep-21 (hidden)
Tentative Planned Outages for the month of September-2021 of Hospet Urban
Name of Division | Name of Subdivision | Name of SubStation | Name of Feeder | Feeder Code | Feeder Type | Date | Outage From | Outage To | Duration Of Outage | Outage Type | Area Affected | Reason of Outage
Hosapete Urban | USD-1 | 33KV MUSS, HOSAPETE | F-5 AMARAVATHI FEEDER | 40020575589 | URBAN | 6.09.2021 | 10:00:00AM | 01:00:00PM | 3Hours | Scheduled maintainance | Industrial area, Rajeev Nagar, Chittawadigi, Amaravathi, Sai Ram Badavane, Kalyan Nagar, Mallinath Layout | Jungle cutting & line GOS maintainance
| USD-1 | 33KV MUSS, HOSAPETE | F-4 Ennoble | 40020575583 | URBAN | 4.09.2021 | 10:00:00AM | 01:00:00PM | 3Hours | Scheduled maintainance | Indira Nagar, Rayal orchid Hotel | Line GOS Maintainance
| USD-1 | 110KV Sanklapura | F-11 TSP | 40020575598 | URBAN | 7.09.2021 | 10:00:00AM | 01:00:00PM | 3Hours | Scheduled maintainance | TB Dam, Gokul Nagar, Sonia Nagar | Line GOS Maintainance
| USD-1 | 33KV MUSS, HOSAPETE | F-10 Patel Nagar | 40020575588 | URBAN | 8.09.2021 | 10:00:00AM | 01:00:00PM | 3Hours | Scheduled maintainance | Chapal Gadda, Patel Nagar, Station Road | Jungle Cutting
| USD-2 | 110KV MUSS SANKALAPURA | F6-SANKALAPURA | 40020575592 | URBAN | 14.09.2021 | 10:00:00AM | 01:00:00PM | 3Hours | SCHELDULED | SANKALAPURA,KARIRNOOR | GOS MAINTENANCE
| RSD | Hosapete Rural | 110/11KV MUSS Sanklapura | F-5Basavanadurga | NJY | 05.09.2021 | 11:00:00PM | 01:00:00PM | 2 Hours | Scheduled | Kakubalu, GV Gere, Pk Halli & Vaddarahalli | Jungle Cutting
| RSD | Hosapete Rural | 110/11KV MUSS Sanklapura | F-7 P.K.Halli | IP | 08.09.2021 | 10:30:00PM | 12:30:00PM | 1 Hour | Scheduled | Kakubalu, GV Gere, Kallahalli & Rajapura | DTC Mantainance
| RSD | Hosapete Rural | 110/11KV MUSS Sanklapura | F-7 B.V.gere | IP | 10.09.2021 | 10:00:00AM | 11:00:00AM | 1 Hour | Scheduled | Nagenahalli, Hosuru, Basavanadurga, Benakapura | 11KV GOS Mantanance
| RSD | Hosapete Rural | 110/11KV MUSS Kamalapura | F-13 Rajapura | NJY | 15.09.2021 | 11:30:00AM | 12:30:00PM | 1 Hour | Scheduled | PK Halli, Vadrahalli, BV Gere | Stringing of 11KV Loose Spans
| RSD | Hosapete Rural | 110/11KV MUSS Kamalapura | F-13 Hostel | NJY | 20.09.2021 | 10:00:00AM | 1:00:00PM | 3Hours | Scheduled | PK Halli, Vadrahalli, BV Gere , Gadiganuru, Dharmasagara & Bhuvanahalli | Replacement of Damaged Poles
| RSD | M.M.Halli | 66/11KV Venkatapura | F-1 M.M.Halli | Urban | 06.09.2021 | 9:00:00AM | 11:00:00AM | 2 Hours | Scheduled | M.M.Halli Town & Nandibandi Pumpset | Jungle Cutting & Insulater Manatanance
| RSD | M.M.Halli | 66/11KV Venkatapura | F-9Thimmalapura | NJY | 10.09.2021 | 10:00:00PM | 01:00:00PM | 3 Houurs | Scheduled | Garaga, Nagalapura, Pothalakatte & TB Thanda ETC | Stringing of 11KV Loose Spans
| RSD | M.M.Halli | 66/11KV Venkatapura | F-2Galemmagudi | NJY | 10.09.2021 | 10:00:00PM | 01:00:00PM | 3 Houurs | Scheduled | Hanumanahalli, Galemmagudi Danapura | GOS Mantanance & Jungle Cutting
| RSD | M.M.Halli | 66/11KV Venkatapura | F-8 Nagalapura | IP | 20.09.2021 | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Gunda, Byalakundi, DN Kere & Gollarahalli | Jungle Cutting
| RSD | M.M.Halli | 66/11KV Venkatapura | F-6 Chilakanahatti | IP | 25.09.2021 | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Haruvanahalli, Chilakanahatti, Thimmalapura & TB Thanda | Jungle Cutting & replacement of Pin Insulater
| RSD | Kampli AE-1 | 110/11KV MUSS Kampli | F-2 Kampli Town | Urban | 08.09.2021 | 09:00:00AM | 11:00:00AM | 2 Hours | Scheduled | Main Bazar, Basavanna Temple, Housing Board Colony, Sn Pet Are | Mantanance Work
| RSD | Kampli AE-1 | 110/11KV MUSS Kampli | F-4 Kampli Kottal | Urban | 08.09.2021 | 10:00:00AM | 12:00:00PM | 2 Hours | Scheduled | Vinayaka Nagara, Idira Nagara, Sanapura Road, Kottal Road | DTC Wiring
| RSD | Kampli AE-1 | 110/11KV MUSS Kampli | F-3 Industrial | Urban | 15.09.2021 | 09:00:00AM | 01:00:00PM | 4Hours | Scheduled | Kottal | GOS Mantanance
| RSD | Kampli AE-1 | 110/11KV MUSS Kampli | F-12 Basaveshwara Nagara | Urban | 20.09.2021 | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Basaveshwara Nagara, Maruthi Nagara | Line Mantanance
| RSD | Kampli AE-1 | 110/11KV MUSS Kampli | F-13 Prabhu Camp | Urban | 25.09.2021 | 10:00:00AM | 12:00:00PM | 2 Hours | Scheduled | Sugar Factory, Prabhu Camp, Huligemma Camp | Line Mantanance
| RSD | Kamalapura | 110/11KV MUSS Kamalapura | F-12 Kamalapura Town | Urban | 05.09.2021 | 09:00:00AM | 12:00:00PM | 3 Hours | Scheduled | Kamalapura Town | Jungle Cutting
| RSD | Kamalapura | 110/11KV MUSS Kamalapura | F-3 Nallapura | NJY | 09.09.2021 | 09:00:00AM | 12:00:00PM | 3 Hours | Scheduled | Nallapura, Hosa Chinnapura SR Thanda | GOS Mantanance
| RSD | Kamalapura | 110/11KV MUSS Kamalapura | F-2 Malapanagudi | Rural | 14.09.2021 | 11:00:00AM | 06:00:00PM | 7 Hours | Scheduled | Hosa Malapanagudi, galemmagudi | Stringing of 11KV Loose Spans
| RSD | Kamalapura | 110/11KV MUSS Kamalapura | F-4 University | Rural | 18.09.2021 | 12:00:00AM | 02:00:00PM | 2 Hours | Scheduled | University, Nallapura | GOS Mantanance & Jungle Cutting
| RSD | Kampli AE-2 | 110/11KV MUSS Kampli | F-6 Vidyapeeta | NJY | 06.09.2021 | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Ramasagara, Kanavi Thimmalapura | Jungle Cuuting
| RSD | Kampli AE-2 | 110/11KV MUSS Kampli | F-8 KT Pura | IP | 06.09.2021 | 07:00:00AM | 10:00:00PM | 3 Houurs | Scheduled | KT Pura Gouramma kere | Jungle Cuuting
| RSD | Kampli AE-2 | 110/11KV MUSS Kampli | F-3 Belagodhal | IP | 14.09.2021 | 10:00:00PM | 02:00:00PM | 4 Houurs | Scheduled | Belagodhal | Jungle Cuuting

## Oct-21 (hidden)
Tentative Planned Outages for the month of October-2021 of Hospet Urban
Name of Division | Name of Subdivision | Name of SubStation | Name of Feeder | Feeder Code | Feeder Type | Date | Outage From | Outage To | Duration Of Outage | Outage Type | Area Affected | Reason of Outage
Hosapete Urban | USD-1 | 33KV MUSS, HOSAPETE | F-5 AMARAVATHI FEEDER | 40020575589 | URBAN | 5.10.2021 | 10:00:00AM | 01:00:00PM | 3 Houurs | Scheduled maintainance | Industrial area, Rajeev Nagar, Chittawadigi, Amaravathi, Sai Ram Badavane, Kalyan Nagar, Mallinath Layout | Jungle cutting & line GOS maintainance
| USD-1 | 33KV MUSS, HOSAPETE | F-10 Patel Nagar | 40020575588 | URBAN | 8.10.2021 | 10:00:00AM | 01:00:00PM | 3 Houurs | Scheduled maintainance | Indira Nagar, Rayal orchid Hotel | Line GOS Maintainance
| USD-2 | 110KV MUSS SANKALAPURA | F8-MP.PRAKASH NAGAR | 40020575601 | URBAN | 6.10.2021 | 10:30:00PM | 01:30:00PM | 3 Houurs | SCHELDULED | MP.PRAKASH NAGAR, SANKALAPURA, A.S.GUDI, SAI COLONY, KN.HALLI | GOS MAINTENANCE AND JUNGLE CUTTING
| USD-2 | 33KV MUSS | F11 HAMPI ROAD | 40020575584 | URBAN | 22.10.2021 | 10:30:00PM | 01:30:00PM | 3 Houurs | SCHELDULED | SUNNADA BHAATTI , JAIN COLONY , HAMPI ROAD, | GOS MAINTENANCE
| RSD | Kampli AE-1 | 110/11KV MUSS Kampli | F-2Kampli Town | Urban | 08.10.2021 | 11:00:00PM | 01:00:00PM | 2 Hours | Scheduled | Kakubalu, GV Gere, Pk Halli & Vaddarahalli | Jungle Cutting
| RSD | Kampli AE-1 | 110/11KV MUSS Kampli | F-4Kampli Kottal | Urban | 10.10.2021 | 10:30:00PM | 12:30:00PM | 1 Hour | Scheduled | Kakubalu, GV Gere, Kallahalli & Rajapura | DTC Mantainance
| RSD | Kampli AE-1 | 110/11KV MUSS Kampli | F-3Industrial | Urban | 15.10.201 | 10:00:00AM | 11:00:00AM | 1 Hour | Scheduled | Nagenahalli, Hosuru, Basavanadurga, Benakapura | 11KV GOS Mantanance
| RSD | Kampli AE-1 | 110/11KV MUSS Kampli | F-12 Basaveshwara Nagara | Urban | 16.10.2021 | 11:30:00AM | 12:30:00PM | 1 Hour | Scheduled | PK Halli, Vadrahalli, BV Gere | Stringing of 11KV Loose Spans
| RSD | Kampli AE-1 | 110/11KV MUSS Kampli | F-13Prabhu Camp | Urban | 20.10.2021 | 10:00:00AM | 1:00:00PM | 3Hours | Scheduled | PK Halli, Vadrahalli, BV Gere , Gadiganuru, Dharmasagara & Bhuvanahalli | Replacement of Damaged Poles
| RSD | Kamalapura | 110/11KV MUSS Kamalapura | F-12 Kamalapura Town | Urban | 06.10.2021 | 9:00:00AM | 11:00:00AM | 2 Hours | Scheduled | M.M.Halli Town & Nandibandi Pumpset | Jungle Cutting & Insulater Manatanance
| RSD | Kamalapura | 110/11KV MUSS Kamalapura | F-3Nallapura | NJY | 10.10.2021 | 10:00:00PM | 01:00:00PM | 3 Houurs | Scheduled | Garaga, Nagalapura, Pothalakatte & TB Thanda ETC | Stringing of 11KV Loose Spans
| RSD | Kamalapura | 110/11KV MUSS Kamalapura | F-2 Malapanagudi | Rural | 10.10.2021 | 10:00:00PM | 01:00:00PM | 3 Houurs | Scheduled | Hanumanahalli, Galemmagudi Danapura | GOS Mantanance & Jungle Cutting
| RSD | Kamalapura | 110/11KV MUSS Kamalapura | F-4 University | Rural | 15.10.2021 | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Gunda, Byalakundi, DN Kere & Gollarahalli | Jungle Cutting
| RSD | Kampli AE-2 | 110/11KV MUSS Kampli | F-6Vidyapeeta | NJY | 25.10.2021 | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Haruvanahalli, Chilakanahatti, Thimmalapura & TB Thanda | Jungle Cutting & replacement of Pin Insulater
| RSD | Kampli AE-2 | 110/11KV MUSS Kampli | F-8 KT Pura | IP | 08.10.2021 | 09:00:00AM | 11:00:00AM | 2 Hours | Scheduled | Main Bazar, Basavanna Temple, Housing Board Colony, Sn Pet Are | Mantanance Work
| RSD | Kampli AE-2 | 110/11KV MUSS Kampli | F-3 Belagodhal | IP | 08.10.2021 | 10:00:00AM | 12:00:00PM | 2 Hours | Scheduled | Vinayaka Nagara, Idira Nagara, Sanapura Road, Kottal Road | DTC Wiring
| RSD | Hosapete Rural | 110/11KV MUSS Sanklapura | F-5Basavanadurga | NJY | 09.10.2021 | 09:00:00AM | 01:00:00PM | 4Hours | Scheduled | Kottal | GOS Mantanance
| RSD | Hosapete Rural | 110/11KV MUSS Sanklapura | F-7P.K.Halli | IP | 11.1.0.2021 | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Basaveshwara Nagara, Maruthi Nagara | Line Mantanance
| RSD | Hosapete Rural | 110/11KV MUSS Sanklapura | F-7 B.V.gere | IP | 14.10.2021 | 10:00:00AM | 12:00:00PM | 2 Hours | Scheduled | Sugar Factory, Prabhu Camp, Huligemma Camp | Line Mantanance
| RSD | Hosapete Rural | 110/11KV MUSS Kamalapura | F-13Rajapura | NJY | 16.10.2021 | 09:00:00AM | 12:00:00PM | 3 Hours | Scheduled | Kamalapura Town | Jungle Cutting
| RSD | Hosapete Rural | 110/11KV MUSS Kamalapura | F-13Hostel | NJY | 18.10.2021 | 09:00:00AM | 12:00:00PM | 3 Hours | Scheduled | Nallapura, Hosa Chinnapura SR Thanda | GOS Mantanance
| RSD | M.M.Halli | 66/11KV Venkatapura | F-1 M.M.Halli | Urban | 9.10.2021 | 11:00:00AM | 06:00:00PM | 7 Hours | Scheduled | Hosa Malapanagudi, galemmagudi | Stringing of 11KV Loose Spans
| RSD | M.M.Halli | 66/11KV Venkatapura | F-9 Thimmalapura | NJY | 11.10.2021 | 12:00:00AM | 02:00:00PM | 2 Hours | Scheduled | University, Nallapura | GOS Mantanance & Jungle Cutting
| RSD | M.M.Halli | 66/11KV Venkatapura | F-2Galemmagudi | NJY | 14.10.2021 | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Ramasagara, Kanavi Thimmalapura | Jungle Cuuting
| RSD | M.M.Halli | 66/11KV Venkatapura | F-8Nagalapura | IP | 15.10.2021 | 07:00:00AM | 10:00:00PM | 3 Houurs | Scheduled | KT Pura Gouramma kere | Jungle Cuuting
| RSD | M.M.Halli | 66/11KV Venkatapura | F-6Chilakanahatti | IP | 18.10.2021 | 10:00:00PM | 02:00:00PM | 4 Houurs | Scheduled | Belagodhal | Jungle Cuuting

## Nov- 21 (hidden)
Tentative Planned Outages for the month of Nov-2021 of Hospet Urban
Name of Division | Name of Subdivision | Name of SubStation | Name of Feeder | Feeder Code | Feeder Type | Date | Outage From | Outage To | Duration Of Outage | Outage Type | Area Affected | Reason of Outage
Hosapete Urban | USD-1 | 33KV MUSS, HOSAPETE | F-5 AMARAVATHI FEEDER | 40020575589 | URBAN | 8.11.2021 | 10.00 AM | 1.00 PM | 3.00 HRS | Scheduled maintainance | Industrial area, Rajeev Nagar, Chittawadigi, Amaravathi, Sai Ram Badavane, Kalyan Nagar, Mallinath Layout | Jungle cutting & line GOS maintainance
| USD-1 | 33KV MUSS, HOSAPETE | F-9Chinthamani | 40020575587 | URBAN | 9.11.2021 | 10.00 AM | 1.00 PM | 3.00 HRS | Scheduled maintainance | Amaravathi, IB, College Road | Line GOS Maintainance
| USD-1 | 33KV MUSS, HOSAPETE | F-10 Patel Nagar | 40020575588 | URBAN | 10.11.2021 | 10.00 AM | 1.00 PM | 3.00 HRS | Scheduled maintainance | Chapal Gadda, Patel Nagar, Station Road | Line GOS Maintainance
| USD-1 | 110KV Sanklapura | F-9 NC COLONY | 40020575600 | URBAN | 11.11.2021 | 10.00 AM | 1.00 PM | 3.00 HRS | Scheduled maintainance | Chapparadahalli, Harihara Road, Gandhi Colony, Vivekananda Nagar, Sandur Road, Dam Road | Jungle cutting & line GOS maintainance
| USD-1 | 110KV Sanklapura | F-11 TSP | 40020575598 | URBAN | 13.11.2021 | 10.00 AM | 1.00 PM | 3.00 HRS | Scheduled maintainance | TB Dam, Gokul Nagar, Sonia Nagar | Jungle cutting & line GOS maintainance
| USD-2 | 110KV MUSS SANKALAPURA | F6-Sankalapura | 40020575601 | URBAN | 9.11.2021 | 10:30 | 15:30 | 3 | SCHELDULED | Sankalapura village, sankalapura thanda, bellary road, Ayurvedic college | GOS Alignment MAINTENANCE AND JUNGLE CUTTING Work
| USD-2 | 110KV MUSS SANKALAPURA | F15-jambunath gudi | 40020575602 | URBAN | 12.11.2021 | 10:00 | 15:00 | 3:00 | SCHELDULED | J.N.Halli, J,N,Road | GOS AligntmentMAINTENANCE
| USD-2 | 33KV MUSS | F3- Hospet City | 40020575593 | URBAN | 16.11.2021 | 10:00 | 15:00 | 3:00 | SCHELDULED | Sirisinakallu, Bellary Road, Arvind Nagar, Bus Depo Area, Ukkadakeri | GOS Alignment MAINTENANCE
| USD-2 | 33KV MUSS | F1-Rama Feeder | 40020575594 | URBAN | 29.11.2021 | 10:00 | 15:00 | 3:00 | SCHELDULED | N.C.Colony, Akashveni Area, Rama Area, Mysankeri | Jungle Cutting
| RSD | 110/11KV MUSS Sanklapura | Basavanadurga | F5 | NJY | 14.11.2021 | 11:00:00PM | 01:00:00PM | 2 Hours | Scheduled | Kakubalu, GV Gere, Pk Halli & Vaddarahalli | Jungle Cutting
| RSD | 110/11KV MUSS Sanklapura | P.K.Halli | F7 | IP | 18.11.2021 | 10:30:00PM | 12:30:00PM | 1 Hour | Scheduled | Kakubalu, GV Gere, Kallahalli & Rajapura | DTC Mantainance
| RSD | 110/11KV MUSS Sanklapura | B.V.gere | F7 | IP | 20.11.2021 | 10:00:00AM | 11:00:00AM | 1 Hour | Scheduled | Nagenahalli, Hosuru, Basavanadurga, Benakapura | 11KV GOS Mantanance
| RSD | 110/11KV MUSS Kamalapura | Rajapura | F13 | NJY | 25.11.2021 | 11:30:00AM | 12:30:00PM | 1 Hour | Scheduled | PK Halli, Vadrahalli, BV Gere | Stringing of 11KV Loose Spans
| RSD | 110/11KV MUSS Kamalapura | Hostel | F13 | NJY | 27.11.2021 | 10:00:00AM | 1:00:00PM | 3Hours | Scheduled | PK Halli, Vadrahalli, BV Gere , Gadiganuru, Dharmasagara & Bhuvanahalli | Replacement of Damaged Poles
| RSD | 66/11KV Venkatapura | M.M.Halli | F1 | Urban | 12.11.2021 | 9:00:00AM | 11:00:00AM | 2 Hours | Scheduled | M.M.Halli Town & Nandibandi Pumpset | Jungle Cutting & Insulater Manatanance
| RSD | 66/11KV Venkatapura | Thimmalapura | F9 | NJY | 15.11.2021 | 10:00:00PM | 01:00:00PM | 3 Houurs | Scheduled | Garaga, Nagalapura, Pothalakatte & TB Thanda ETC | Stringing of 11KV Loose Spans
| RSD | 66/11KV Venkatapura | Galemmagudi | F2 | NJY | 16.11.2021 | 10:00:00PM | 01:00:00PM | 3 Houurs | Scheduled | Hanumanahalli, Galemmagudi Danapura | GOS Mantanance & Jungle Cutting
| RSD | 66/11KV Venkatapura | Nagalapura | F8 | IP | 22.11.2021 | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Gunda, Byalakundi, DN Kere & Gollarahalli | Jungle Cutting
| RSD | 66/11KV Venkatapura | Chilakanahatti | F6 | IP | 25.11.2021 | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Haruvanahalli, Chilakanahatti, Thimmalapura & TB Thanda | Jungle Cutting & replacement of Pin Insulater
| RSD | 110/11KV MUSS Kampli | Kampli Town | F2 | Urban | 13.11.2021 | 09:00:00AM | 11:00:00AM | 2 Hours | Scheduled | Main Bazar, Basavanna Temple, Housing Board Colony, Sn Pet Are | Mantanance Work
| RSD | 110/11KV MUSS Kampli | Kampli Kottal | F4 | Urban | 15.11.2021 | 10:00:00AM | 12:00:00PM | 2 Hours | Scheduled | Vinayaka Nagara, Idira Nagara, Sanapura Road, Kottal Road | DTC Wiring
| RSD | 110/11KV MUSS Kampli | Industrial | F3 | Urban | 18.11.2021 | 09:00:00AM | 01:00:00PM | 4Hours | Scheduled | Kottal | GOS Mantanance
| RSD | 110/11KV MUSS Kampli | Basaveshwara Nagara | F12 | Urban | 20.11.2021 | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Basaveshwara Nagara, Maruthi Nagara | Line Mantanance
| RSD | 110/11KV MUSS Kampli | Prabhu Camp | F13 | Urban | 30.11.2021 | 10:00:00AM | 12:00:00PM | 2 Hours | Scheduled | Sugar Factory, Prabhu Camp, Huligemma Camp | Line Mantanance
| RSD | 110/11KV MUSS Kamalapura | Kamalapura Town | F12 | Urban | 16.11.2021 | 09:00:00AM | 12:00:00PM | 3 Hours | Scheduled | Kamalapura Town | Jungle Cutting
| RSD | 110/11KV MUSS Kamalapura | Nallapura | F3 | NJY | 18.11.2021 | 09:00:00AM | 12:00:00PM | 3 Hours | Scheduled | Nallapura, Hosa Chinnapura SR Thanda | GOS Mantanance
| RSD | 110/11KV MUSS Kamalapura | Malapanagudi | F2 | Rural | 22.11.2021 | 11:00:00AM | 06:00:00PM | 7 Hours | Scheduled | Hosa Malapanagudi, galemmagudi | Stringing of 11KV Loose Spans
| RSD | 110/11KV MUSS Kamalapura | University | F4 | Rural | 26.11.2021 | 12:00:00AM | 02:00:00PM | 2 Hours | Scheduled | University, Nallapura | GOS Mantanance & Jungle Cutting
| RSD | 110/11KV MUSS Kampli | Vidyapeeta | F6 | NJY | 14.11.2021 | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Ramasagara, Kanavi Thimmalapura | Jungle Cuuting
| RSD | 110/11KV MUSS Kampli | KT Pura | F8 | IP | 16.11.2021 | 07:00:00AM | 10:00:00PM | 3 Houurs | Scheduled | KT Pura Gouramma kere | Jungle Cuuting
| RSD | 110/11KV MUSS Kampli | Belagodhal | F3 | IP | 28.11.2021 | 10:00:00PM | 02:00:00PM | 4 Houurs | Scheduled | Belagodhal | Jungle Cuuting

## Dec-21 (hidden)
Tentative Planned Outages for the month of DEC-2021 of Hospet Urban
Name of Division | Name of Subdivision | Name of SubStation | Name of Feeder | Feeder Code | Feeder Type | Date | Outage From | Outage To | Duration Of Outage | Outage Type | Area Affected | Reason of Outage
Hosapete Urban | USD-1 | 33KV MUSS, HOSAPETE | F-5 AMARAVATHI FEEDER | 40020575589 | URBAN | 8.12.2021 | 10.00 AM | 1.00 PM | 3.00 HRS | Scheduled maintainance | Industrial area, Rajeev Nagar, Chittawadigi, Amaravathi, Sai Ram Badavane, Kalyan Nagar, Mallinath Layout | Line GOS Maintainance
| USD-1 | 33KV MUSS, HOSAPETE | F-9Chinthamani | 40020575587 | URBAN | 9.12.2021 | 10.00 AM | 1.00 PM | 3.00 HRS | Scheduled maintainance | Amaravathi, IB, College Road | Jungle cutting & line GOS maintainance
| USD-1 | 33KV MUSS, HOSAPETE | F-10 Patel Nagar | 40020575588 | URBAN | 10.12.2021 | 10.00 AM | 1.00 PM | 3.00 HRS | Scheduled maintainance | Chapal Gadda, Patel Nagar, Station Road | Jungle cutting & line GOS maintainance
| USD-1 | 110KV Sanklapura | F-9 NC COLONY | 40020575600 | URBAN | 10.12.2021 | 10.00 AM | 1.00 PM | 3.00 HRS | Scheduled maintainance | Chapparadahalli, Harihara Road, Gandhi Colony, Vivekananda Nagar, Sandur Road, Dam Road | Line GOS Maintainance
| USD-1 | 110KV Sanklapura | F-11 TSP | 40020575598 | URBAN | 13.12.2021 | 10.00 AM | 1.00 PM | 3.00 HRS | Scheduled maintainance | TB Dam, Gokul Nagar, Sonia Nagar | Line GOS Maintainance
| USD-2 | 110KV MUSS SANKALAPURA | F1-Rama Feeder | 40020575594 | URBAN | 6.12.2021 | 10:00 | 14:00 | 4:00 | SCHELDULED | PARVATHI NAGAR, AKASHVANI, N.C.COLONY, MYASAKERI, TALVALKERI, CHITTARKERI, OLD VEGTABLE MARKET, COWL PETE, S.R.NAGAR, CHALUVADIKERI, A C OFFICE | GOS AligntmentMAINTENANCE
| USD-2 | 110KV MUSS SANKALAPURA | F11-HAMPI | 40020575584 | URBAN | 7.12.2021 | 10:00 | 14:00 | 4:00 | SCHELDULED | Hampi Road, BUS STAND ROAD, NAGENAHALI ROAD, 3 SHOP CIRCLE, BALA TALKIES, CMC | Jungle Cutting
| USD-2 | 33KV MUSS | F6-BELLARY ROAD | 40020575586 | URBAN | 08.12.2021 | 10:00 | 14:00 | 4:00 | SCHELDULED | GOWLLARATTI, RANIPETE, COURT AREA, MEERALAM TALKIES AREA | Jungle Cutting
| USD-2 | 33KV MUSS | F4-KOF | 40020575591 | URBAN | 09.12.2021 | 10:00 | 14:00 | 4:00 | SCHELDULED | KIADB INDUSTRAIL AREA SANKALAPURA | GOS Alignment MAINTENANCE AND JUNGLE CUTTING Work
| RSD | 110/11KV MUSS Sanklapura | Basavanadurga | F5 | NJY | 13.12.2021 | 09:00:00AM | 11:00:00AM | 2 Hours | Scheduled | Main Bazar, Basavanna Temple, Housing Board Colony, Sn Pet Are | Jungle Cutting
| RSD | 110/11KV MUSS Sanklapura | P.K.Halli | F7 | IP | 15.12.2021 | 10:00:00AM | 12:00:00PM | 2 Hours | Scheduled | Vinayaka Nagara, Idira Nagara, Sanapura Road, Kottal Road | DTC Mantainance
| RSD | 110/11KV MUSS Sanklapura | B.V.gere | F7 | IP | 18.12.2021 | 09:00:00AM | 01:00:00PM | 4Hours | Scheduled | Kottal | 11KV GOS Mantanance
| RSD | 110/11KV MUSS Kamalapura | Rajapura | F13 | NJY | 20.12.2021 | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Basaveshwara Nagara, Maruthi Nagara | Stringing of 11KV Loose Spans
| RSD | 110/11KV MUSS Kamalapura | Hostel | F13 | NJY | 30.12.2021 | 10:00:00AM | 12:00:00PM | 2 Hours | Scheduled | Sugar Factory, Prabhu Camp, Huligemma Camp | Replacement of Damaged Poles
| RSD | 66/11KV Venkatapura | M.M.Halli | F1 | Urban | 16.12.2021 | 09:00:00AM | 12:00:00PM | 3 Hours | Scheduled | Kamalapura Town | Jungle Cutting & Insulater Manatanance
| RSD | 66/11KV Venkatapura | Thimmalapura | F9 | NJY | 18.12.2021 | 09:00:00AM | 12:00:00PM | 3 Hours | Scheduled | Nallapura, Hosa Chinnapura SR Thanda | Stringing of 11KV Loose Spans
| RSD | 66/11KV Venkatapura | Galemmagudi | F2 | NJY | 22.12.2021 | 11:00:00AM | 06:00:00PM | 7 Hours | Scheduled | Hosa Malapanagudi, galemmagudi | GOS Mantanance & Jungle Cutting
| RSD | 66/11KV Venkatapura | Nagalapura | F8 | IP | 26.12.2021 | 12:00:00AM | 02:00:00PM | 2 Hours | Scheduled | University, Nallapura | Jungle Cutting
| RSD | 66/11KV Venkatapura | Chilakanahatti | F6 | IP | 30.12.2021 | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Ramasagara, Kanavi Thimmalapura | Jungle Cutting & replacement of Pin Insulater
| RSD | 110/11KV MUSS Kampli | Kampli Town | F2 | Urban | 14.12.2021 | 11:00:00PM | 01:00:00PM | 2 Hours | Scheduled | Kakubalu, GV Gere, Pk Halli & Vaddarahalli | Jungle Cutting
| RSD | 110/11KV MUSS Kampli | Kampli Kottal | F4 | Urban | 18.12.2021 | 10:30:00PM | 12:30:00PM | 1 Hour | Scheduled | Kakubalu, GV Gere, Kallahalli & Rajapura | DTC Mantainance
| RSD | 110/11KV MUSS Kampli | Industrial | F3 | Urban | 20.12.2021 | 10:00:00AM | 11:00:00AM | 1 Hour | Scheduled | Nagenahalli, Hosuru, Basavanadurga, Benakapura | 11KV GOS Mantanance
| RSD | 110/11KV MUSS Kampli | Basaveshwara Nagara | F12 | Urban | 25.12.2021 | 11:30:00AM | 12:30:00PM | 1 Hour | Scheduled | PK Halli, Vadrahalli, BV Gere | Stringing of 11KV Loose Spans
| RSD | 110/11KV MUSS Kampli | Prabhu Camp | F13 | Urban | 27.12.2021 | 10:00:00AM | 1:00:00PM | 3Hours | Scheduled | PK Halli, Vadrahalli, BV Gere , Gadiganuru, Dharmasagara & Bhuvanahalli | Replacement of Damaged Poles
| RSD | 110/11KV MUSS Kamalapura | Kamalapura Town | F12 | Urban | 12.12.2021 | 9:00:00AM | 11:00:00AM | 2 Hours | Scheduled | M.M.Halli Town & Nandibandi Pumpset | Jungle Cutting & Insulater Manatanance
| RSD | 110/11KV MUSS Kamalapura | Nallapura | F3 | NJY | 15.12.2021 | 10:00:00PM | 01:00:00PM | 3 Houurs | Scheduled | Garaga, Nagalapura, Pothalakatte & TB Thanda ETC | Stringing of 11KV Loose Spans
| RSD | 110/11KV MUSS Kamalapura | Malapanagudi | F2 | Rural | 16.12.2021 | 10:00:00PM | 01:00:00PM | 3 Houurs | Scheduled | Hanumanahalli, Galemmagudi Danapura | GOS Mantanance & Jungle Cutting
| RSD | 110/11KV MUSS Kamalapura | University | F4 | Rural | 22.12.2021 | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Gunda, Byalakundi, DN Kere & Gollarahalli | Jungle Cutting
| RSD | 110/11KV MUSS Kampli | Vidyapeeta | F6 | NJY | 15.12.2021 | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Haruvanahalli, Chilakanahatti, Thimmalapura & TB Thanda | Jungle Cutting & replacement of Pin Insulater
| RSD | 110/11KV MUSS Kampli | KT Pura | F8 | IP | 16.12.2021 | 07:00:00AM | 10:00:00PM | 3 Houurs | Scheduled | KT Pura Gouramma kere | Jungle Cuuting
| RSD | 110/11KV MUSS Kampli | Belagodhal | F3 | IP | 22.12.2021 | 10:00:00PM | 02:00:00PM | 4 Houurs | Scheduled | Belagodhal | Jungle Cuuting

## Jan-22 (hidden)
Tentative Planned Outages for the month of January-2022 of Hospet Urban
Name of Division | Name of Subdivision | Name of SubStation | Name of Feeder | Feeder Code | Feeder Type | Date | Outage From | Outage To | Duration Of Outage | Outage Type | Area Affected | Reason of Outage
Hosapete Urban | USD-1 | 33KV MUSS, HOSAPETE | F-1 Station Road FEEDER | 40020575590 | URBAN | 07.12.2021 | 10:00:00AM | 01:00:00PM | 3.00 HRS | Scheduled | Basaveshwara Badavane, College Road, Chittawadigi, Jabbal Area | Jungle cutting & line GOS maintainance
| USD-1 | 33KV MUSS, HOSAPETE | F-9Chinthamani | 40020575587 | URBAN | 10.12.2021 | 10:00:00AM | 01:00:00PM | 3.00 HRS | Scheduled | Amaravathi, IB, College Road | Line GOS Maintainance
| USD-1 | 33KV MUSS, HOSAPETE | F-10 Patel Nagar | 40020575588 | URBAN | 12.01.2021 | 10:00:00AM | 01:00:00PM | 3.00 HRS | Scheduled | Chapal Gadda, Patel Nagar, Station Road | Line GOS Maintainance
| USD-1 | 110KV Sanklapura | F-9 NC COLONY | 40020575600 | URBAN | 07.01.2021 | 10:00:00AM | 01:00:00PM | 3.00 HRS | Scheduled | Chapparadahalli, Harihara Road, Gandhi Colony, Vivekananda Nagar, Sandur Road, Dam Road | Jungle cutting & line GOS maintainance
| USD-1 | 110KV Sanklapura | F-11 TSP | 40020575598 | URBAN | 10.12.2021 | 10:00:00AM | 01:00:00PM | 3.00 HRS | Scheduled | TB Dam, Gokul Nagar, Sonia Nagar | Jungle cutting & line GOS maintainance
| USD-2 | 110KV MUSS SANKALAPURA | F8-M.P.PRAKASH MAGAR | 40020575601 | URBAN | 08.12.2021 | 10:00:00AM | 14:00 | 4:00 | Scheduled | MP.PRAKASH NAGAR, SANKALAPURA, A.S.GUDI, SAI COLONY, KN.HALLI | JUNGLE CUTTING WORK
| USD-3 | 110KV MUSS SANKALAPURA | F6-Sankalapura | 40020575592 | URBAN | 09.12.2021 | 10:30:00AM | 15:30 | 3 | Scheduled | Sankalapura village, sankalapura thanda, bellary road, Ayurvedic college | GOS Alignment MAINTENANCE AND JUNGLE CUTTING Work
| USD-4 | 33KV MUSS | F6-BELLARY ROAD | 40020575586 | URBAN | 08.12.2021 | 10:00:00AM | 15:00 | 3:00 | Scheduled | GOWLLARATTI, RANIPETE, COURT AREA, MEERALAM TALKIES AREA | GOS AligntmentMAINTENANCE
| RSD | 110/11KV MUSS Kampli | Kampli Town | F2 | Urban | 13.01.2022 | 09:00:00AM | 11:00:00AM | 2 Hours | Scheduled | Main Bazar, Basavanna Temple, Housing Board Colony, Sn Pet Are | Mantanance Work
| RSD | 110/11KV MUSS Kampli | Kampli Kottal | F4 | Urban | 15.01.2022 | 10:00:00AM | 12:00:00PM | 2 Hours | Scheduled | Vinayaka Nagara, Idira Nagara, Sanapura Road, Kottal Road | DTC Wiring
| RSD | 110/11KV MUSS Kampli | Industrial | F3 | Urban | 18.01.2022 | 09:00:00AM | 01:00:00PM | 4Hours | Scheduled | Kottal | GOS Mantanance
| RSD | 110/11KV MUSS Kampli | Basaveshwara Nagara | F12 | Urban | 20.01.2022 | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Basaveshwara Nagara, Maruthi Nagara | Line Mantanance
| RSD | 110/11KV MUSS Kampli | Prabhu Camp | F13 | Urban | 30.01.2022 | 10:00:00AM | 12:00:00PM | 2 Hours | Scheduled | Sugar Factory, Prabhu Camp, Huligemma Camp | Line Mantanance
| RSD | 110/11KV MUSS Kamalapura | Kamalapura Town | F12 | Urban | 16.01.2022 | 09:00:00AM | 12:00:00PM | 3 Hours | Scheduled | Kamalapura Town | Jungle Cutting
| RSD | 110/11KV MUSS Kamalapura | Nallapura | F3 | NJY | 18.01.2022 | 09:00:00AM | 12:00:00PM | 3 Hours | Scheduled | Nallapura, Hosa Chinnapura SR Thanda | GOS Mantanance
| RSD | 110/11KV MUSS Kamalapura | Malapanagudi | F2 | Rural | 22.01.2022 | 11:00:00AM | 06:00:00PM | 7 Hours | Scheduled | Hosa Malapanagudi, galemmagudi | Stringing of 11KV Loose Spans
| RSD | 110/11KV MUSS Kamalapura | University | F4 | Rural | 26.01.2022 | 12:00:00AM | 02:00:00PM | 2 Hours | Scheduled | University, Nallapura | GOS Mantanance & Jungle Cutting
| RSD | 110/11KV MUSS Kampli | Vidyapeeta | F6 | NJY | 14.01.2022 | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Ramasagara, Kanavi Thimmalapura | Jungle Cuuting
| RSD | 110/11KV MUSS Kampli | KT Pura | F8 | IP | 16.01.2022 | 07:00:00AM | 10:00:00PM | 3 Houurs | Scheduled | KT Pura Gouramma kere | Jungle Cuuting
| RSD | 110/11KV MUSS Kampli | Belagodhal | F3 | IP | 28.01.2022 | 10:00:00PM | 02:00:00PM | 4 Houurs | Scheduled | Belagodhal | Jungle Cuuting
| RSD | 110/11KV MUSS Sanklapura | Basavanadurga | F5 | NJY | 6.01.2022 | 11:00:00PM | 01:00:00PM | 2 Hours | Scheduled | Kakubalu, GV Gere, Pk Halli & Vaddarahalli | Jungle Cutting
| RSD | 110/11KV MUSS Sanklapura | P.K.Halli | F7 | IP | 18.01.2022 | 10:30:00PM | 12:30:00PM | 1 Hour | Scheduled | Kakubalu, GV Gere, Kallahalli & Rajapura | DTC Mantainance
| RSD | 110/11KV MUSS Sanklapura | B.V.gere | F7 | IP | 20.01.2022 | 10:00:00AM | 11:00:00AM | 1 Hour | Scheduled | Nagenahalli, Hosuru, Basavanadurga, Benakapura | 11KV GOS Mantanance
| RSD | 110/11KV MUSS Kamalapura | Rajapura | F13 | NJY | 25.01.2022 | 11:30:00AM | 12:30:00PM | 1 Hour | Scheduled | PK Halli, Vadrahalli, BV Gere | Stringing of 11KV Loose Spans
| RSD | 110/11KV MUSS Kamalapura | Hostel | F13 | NJY | 27.01.2022 | 10:00:00AM | 1:00:00PM | 3Hours | Scheduled | PK Halli, Vadrahalli, BV Gere , Gadiganuru, Dharmasagara & Bhuvanahalli | Replacement of Damaged Poles
| RSD | 66/11KV Venkatapura | M.M.Halli | F1 | Urban | 15.01.2022 | 9:00:00AM | 11:00:00AM | 2 Hours | Scheduled | M.M.Halli Town & Nandibandi Pumpset | Jungle Cutting & Insulater Manatanance
| RSD | 66/11KV Venkatapura | Thimmalapura | F9 | NJY | 15.01.2022 | 10:00:00PM | 01:00:00PM | 3 Houurs | Scheduled | Garaga, Nagalapura, Pothalakatte & TB Thanda ETC | Stringing of 11KV Loose Spans
| RSD | 66/11KV Venkatapura | Galemmagudi | F2 | NJY | 16.01.2022 | 10:00:00PM | 01:00:00PM | 3 Houurs | Scheduled | Hanumanahalli, Galemmagudi Danapura | GOS Mantanance & Jungle Cutting
| RSD | 66/11KV Venkatapura | Nagalapura | F8 | IP | 22.01.2022 | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Gunda, Byalakundi, DN Kere & Gollarahalli | Jungle Cutting
| RSD | 66/11KV Venkatapura | Chilakanahatti | F6 | IP | 25.01.2022 | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Haruvanahalli, Chilakanahatti, Thimmalapura & TB Thanda | Jungle Cutting & replacement of Pin Insulater

## FEB-2022 (hidden)
Tentative Planned Outages for the month of February-2022 of Hospet Urban
Name of Division | Name of Subdivision | Name of SubStation | Name of Feeder | Feeder Code | Feeder Type | Date | Outage From | Outage To | Duration Of Outage | Outage Type | Area Affected | Reason of Outage
Hosapete Urban | USD-1 | 33KV MUSS, HOSAPETE | F-5 AMARAVATHI FEEDER | 40020575589 | URBAN | 06.02.2022 | 10:00:00AM | 01:00:00PM | 3 Houurs | Scheduled | Industrial area, Rajeev Nagar, Chittawadigi, Amaravathi, Sai Ram Badavane, Kalyan Nagar, Mallinath Layout | Jungle cutting & line GOS maintainance
| USD-1 | 33KV MUSS, HOSAPETE | F-4 Ennoble | 40020575583 | URBAN | 04.02.2022 | 10:00:00AM | 01:00:00PM | 3 Houurs | Scheduled | Indira Nagar, Rayal orchid Hotel | Line GOS Maintainance
| USD-1 | 110KV Sanklapura | F-11 TSP | 40020575598 | URBAN | 07.02.2022 | 10:00:00AM | 01:00:00PM | 3 Houurs | Scheduled | TB Dam, Gokul Nagar, Sonia Nagar | Line GOS Maintainance
| USD-1 | 33KV MUSS, HOSAPETE | F-10 Patel Nagar | 40020575588 | URBAN | 08.02.2022 | 10:00:00AM | 01:00:00PM | 3 Houurs | Scheduled | Chapal Gadda, Patel Nagar, Station Road | Jungle Cutting
| USD-2 | 33KV MUSS | F3- Hospet City | 40020575593 | URBAN | 07.02.2022 | 10:00:00AM | 01:00:00PM | 3 Houurs | Scheduled | Sirisinakallu, Bellary Road, Arvind Nagar, Bus Depo Area, Ukkadakeri | GOS Alignment MAINTENANCE
| USD-2 | 110KV MUSS SANKALAPURA | F1-Rama Feeder | 40020575594 | URBAN | 08.02.2022 | 10:00:00AM | 02:00:00PM | 4 Houurs | Scheduled | PARVATHI NAGAR, AKASHVANI, N.C.COLONY, MYASAKERI, TALVALKERI, CHITTARKERI, OLD VEGTABLE MARKET, COWL PETE, S.R.NAGAR, CHALUVADIKERI, A C OFFICE | GOS AligntmentMAINTENANCE
| USD-2 | 110KV MUSS SANKALAPURA | F11-HAMPI | 40020575584 | URBAN | 09.02.2022 | 10:00:00AM | 02:00:00PM | 4 Houurs | Scheduled | Hampi Road, BUS STAND ROAD, NAGENAHALI ROAD, 3 SHOP CIRCLE, BALA TALKIES, CMC | Jungle Cutting
| USD-2 | 110KV MUSS SANKALAPURA | F8-MP.PRAKASH NAGAR | 40020575601 | URBAN | 10.02.2022 | 10:00:00AM | 01:00:00PM | 3 Houurs | Scheduled | MP.PRAKASH NAGAR, SANKALAPURA, A.S.GUDI, SAI COLONY, KN.HALLI | GOS MAINTENANCE AND JUNGLE CUTTING
| RSD | 110/11kV Kamalapura | F-12 KAMALAPURA | F12 | URBAN | 2.02.2022 | 10:00:00AM | 01:00:00PM | 3 Houurs | Scheduled | HPC, KAMALAPURA TOUN | GOS Mantanance & Jungle Cutting
| RSD | 110/11kV Kamalapura | F-2 Malapana Gudi | F2 | URBAN | 5.02.2021 | 10:00:00AM | 01:00:00PM | 3 Houurs | Scheduled | GALEMMAGUDI, MALAPANAGUDI | Stringing of 11KV Loose Spans
| RSD | 110/11kV Kamalapura | F-3 Bukkasagara | F3 | EXCLUSIVE IP | 22.02.2022 | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | VENKATAPURA, VENKATAPURA CAMP | GOS Mantanance & Jungle Cutting
| RSD | 110/11kV Kamalapura | F-4 University & crusher | F4 | URBAN | 25.12.2021 | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | UNIVERCITY | Jungle Cutting
| RSD | 110/11kV Kamalapura | F-5 Hampi | F5 | URBAN | 28.12.2021 | 10:00:00AM | 11:00:00AM | 1 Hour | Scheduled | HAMPI VIJAYANAGARA, KD TANDA | Jungle Cutting
| RSD | 110/11KV MUSS Kampli | Kampli Town | F2 | Urban | 13.02.2022 | 09:00:00AM | 11:00:00AM | 2 Hours | Scheduled | Main Bazar, Basavanna Temple, Housing Board Colony, Sn Pet Are | Mantanance Work
| RSD | 110/11KV MUSS Kampli | Kampli Kottal | F4 | Urban | 15.02.2022 | 10:00:00AM | 12:00:00PM | 2 Hours | Scheduled | Vinayaka Nagara, Idira Nagara, Sanapura Road, Kottal Road | DTC Wiring
| RSD | 110/11KV MUSS Kampli | Industrial | F3 | Urban | 18.02.2022 | 09:00:00AM | 01:00:00PM | 4Hours | Scheduled | Kottal | GOS Mantanance
| RSD | 110/11KV MUSS Kampli | Basaveshwara Nagara | F12 | Urban | 20.02.2022 | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Basaveshwara Nagara, Maruthi Nagara | Line Mantanance
| RSD | 110/11KV MUSS Kampli | Prabhu Camp | F13 | Urban | 30.02.2022 | 10:00:00AM | 12:00:00PM | 2 Hours | Scheduled | Sugar Factory, Prabhu Camp, Huligemma Camp | Line Mantanance
| RSD | 110/11KV MUSS Kamalapura | Kamalapura Town | F12 | Urban | 16.02.2022 | 09:00:00AM | 12:00:00PM | 3 Hours | Scheduled | Kamalapura Town | Jungle Cutting
| RSD | 110/11KV MUSS Kamalapura | Nallapura | F3 | NJY | 18.02.2022 | 09:00:00AM | 12:00:00PM | 3 Hours | Scheduled | Nallapura, Hosa Chinnapura SR Thanda | GOS Mantanance
| RSD | 110/11KV MUSS Kamalapura | Malapanagudi | F2 | Rural | 22.02.2022 | 11:00:00AM | 06:00:00PM | 7 Hours | Scheduled | Hosa Malapanagudi, galemmagudi | Stringing of 11KV Loose Spans
| RSD | 110/11KV MUSS Kamalapura | University | F4 | Rural | 26.02.2022 | 12:00:00AM | 02:00:00PM | 2 Hours | Scheduled | University, Nallapura | GOS Mantanance & Jungle Cutting
| RSD | 110/11KV MUSS Kampli | Vidyapeeta | F6 | NJY | 16.02.2022 | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Ramasagara, Kanavi Thimmalapura | Jungle Cuuting
| RSD | 110/11KV MUSS Kampli | KT Pura | F8 | IP | 18.02.2022 | 07:00:00AM | 10:00:00PM | 3 Houurs | Scheduled | KT Pura Gouramma kere | Jungle Cuuting
| RSD | 110/11KV MUSS Kampli | Belagodhal | F3 | IP | 22.02.2022 | 10:00:00PM | 02:00:00PM | 4 Houurs | Scheduled | Belagodhal | Jungle Cuuting
| RSD | 110/11KV MUSS Sanklapura | Basavanadurga | F5 | NJY | 2.02.2022 | 11:00:00PM | 01:00:00PM | 2 Hours | Scheduled | Kakubalu, GV Gere, Pk Halli & Vaddarahalli | Jungle Cutting
| RSD | 110/11KV MUSS Sanklapura | P.K.Halli | F7 | IP | 18.02.2022 | 10:30:00PM | 12:30:00PM | 1 Hour | Scheduled | Kakubalu, GV Gere, Kallahalli & Rajapura | DTC Mantainance
| RSD | 110/11KV MUSS Sanklapura | B.V.gere | F7 | IP | 22.02.2022 | 10:00:00AM | 11:00:00AM | 1 Hour | Scheduled | Nagenahalli, Hosuru, Basavanadurga, Benakapura | 11KV GOS Mantanance
| RSD | 66/11KV Venkatapura | M.M.Halli | F1 | Urban | 1.02.2022 | 9:00:00AM | 11:00:00AM | 2 Hours | Scheduled | M.M.Halli Town & Nandibandi Pumpset | Jungle Cutting & Insulater Manatanance
| RSD | 66/11KV Venkatapura | Thimmalapura | F9 | NJY | 15.02.2022 | 10:00:00PM | 01:00:00PM | 3 Houurs | Scheduled | Garaga, Nagalapura, Pothalakatte & TB Thanda ETC | Stringing of 11KV Loose Spans
| RSD | 66/11KV Venkatapura | Galemmagudi | F2 | NJY | 16.02.2022 | 10:00:00PM | 01:00:00PM | 3 Houurs | Scheduled | Hanumanahalli, Galemmagudi Danapura | GOS Mantanance & Jungle Cutting
| RSD | 66/11KV Venkatapura | Nagalapura | F8 | IP | 22.02.2022 | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Gunda, Byalakundi, DN Kere & Gollarahalli | Jungle Cutting
| RSD | 66/11KV Venkatapura | Chilakanahatti | F6 | IP | 25.02.2022 | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Haruvanahalli, Chilakanahatti, Thimmalapura & TB Thanda | Jungle Cutting & replacement of Pin Insulater

## March-2022 (hidden)
Tentative Planned Outages for the month of Mar-2022 of Hospet Urban
Name of Division | Name of Subdivision | Name of SubStation | Name of Feeder | Feeder Code | DATE | Feeder Type | Outage From | Outage To | Duration Of Outage | Outage Type | Area Affected | Reason of Outage
Hosapete Urban | USD-1 | 33KV MUSS, HOSAPETE | F-5 AMARAVATHI FEEDER | 40020575589 | 2022-03-08 | URBAN | 10.00 AM | 1.00 PM | 3.00 HRS | Scheduled | Industrial area, Rajeev Nagar, Chittawadigi, Amaravathi, Sai Ram Badavane, Kalyan Nagar, Mallinath Layout | Line GOS Maintainance
| USD-1 | 33KV MUSS, HOSAPETE | F-9Chinthamani | 40020575587 | 2022-03-11 | URBAN | 10.00 AM | 1.00 PM | 3.00 HRS | Scheduled | Amaravathi, IB, College Road | Line GOS Maintainance
| USD-1 | 33KV MUSS, HOSAPETE | F-10 Patel Nagar | 40020575588 | 2022-03-15 | URBAN | 10.00 AM | 1.00 PM | 3.00 HRS | Scheduled | Chapal Gadda, Patel Nagar, Station Road | Line GOS Maintainance
| USD-1 | 110KV Sanklapura | F-9 NC COLONY | 40020575600 | 2022-03-08 | URBAN | 10.00 AM | 1.00 PM | 3.00 HRS | Scheduled | Chapparadahalli, Harihara Road, Gandhi Colony, Vivekananda Nagar, Sandur Road, Dam Road | Jungle cutting & line GOS maintainance
| USD-1 | 110KV Sanklapura | F-11 TSP | 40020575598 | 2022-03-11 | URBAN | 10.00 AM | 1.00 PM | 3.00 HRS | Scheduled | TB Dam, Gokul Nagar, Sonia Nagar | Jungle cutting & line GOS maintainance
| USD-2 | 110KV MUSS SANKALAPURA | F8-MP.PRAKASH NAGAR | 40020575601 | 11.03.2022 | URBAN | 10:00 | 13:00 | 3:00 | Scheduled | MP.PRAKASH NAGAR, SANKALAPURA, A.S.GUDI, SAI COLONY, KN.HALLI | GOS MAINTENANCE
| USD-2 | 33KV MUSS | F11 HAMPI ROAD | 40020575584 | 16.03.2022 | URBAN | 10:30 | 14:00 | 0.14583 | Scheduled | SUNNADA BHAATTI , JAIN COLONY , HAMPI ROAD, | GOS MAINTENANCE AND JUNGLE CUTTING
| USD-2 | 110KV MUSS SANKALAPURA | F3- Hospet City | 40020575586 | 23.03.2022 | URBAN | 11:00 | 14:00 | 3:00 | Scheduled | Sirisinakallu, Bellary Road, Arvind Nagar, Bus Depo Area, Ukkadakeri | GOS AligntmentMAINTENANCE
| RSD | 110/11KV MUSS Kampli | Kampli Town | F2 | 13.03.2022 | Urban | 09:00:00AM | 11:00:00AM | 2 Hours | Scheduled | Main Bazar, Basavanna Temple, Housing Board Colony, Sn Pet Are | Mantanance Work
| RSD | 110/11KV MUSS Kampli | Kampli Kottal | F4 | 16.03.2022 | Urban | 10:00:00AM | 12:00:00PM | 2 Hours | Scheduled | Vinayaka Nagara, Idira Nagara, Sanapura Road, Kottal Road | DTC Wiring
| RSD | 110/11KV MUSS Kampli | Industrial | F3 | 18.03.2022 | Urban | 09:00:00AM | 01:00:00PM | 4Hours | Scheduled | Kottal | GOS Mantanance
| RSD | 110/11KV MUSS Kampli | Basaveshwara Nagara | F12 | 21.03.2022 | Urban | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Basaveshwara Nagara, Maruthi Nagara | Line Mantanance
| RSD | 110/11KV MUSS Kampli | Prabhu Camp | F13 | 28.03.2022 | Urban | 10:00:00AM | 12:00:00PM | 2 Hours | Scheduled | Sugar Factory, Prabhu Camp, Huligemma Camp | Line Mantanance
| RSD | 110/11KV MUSS Kamalapura | Kamalapura Town | F12 | 11.03.2022 | Urban | 09:00:00AM | 12:00:00PM | 3 Hours | Scheduled | Kamalapura Town | Jungle Cutting
| RSD | 110/11KV MUSS Kamalapura | Nallapura | F3 | 17.01.2022 | NJY | 09:00:00AM | 12:00:00PM | 3 Hours | Scheduled | Nallapura, Hosa Chinnapura SR Thanda | GOS Mantanance
| RSD | 110/11KV MUSS Kamalapura | Malapanagudi | F2 | 25.03.2022 | Rural | 11:00:00AM | 06:00:00PM | 7 Hours | Scheduled | Hosa Malapanagudi, galemmagudi | Stringing of 11KV Loose Spans
| RSD | 110/11KV MUSS Kamalapura | University | F4 | 28.03.2022 | Rural | 12:00:00AM | 02:00:00PM | 2 Hours | Scheduled | University, Nallapura | GOS Mantanance & Jungle Cutting
| RSD | 110/11KV MUSS Kampli | Vidyapeeta | F6 | 14.03.2022 | NJY | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Ramasagara, Kanavi Thimmalapura | Jungle Cuuting
| RSD | 110/11KV MUSS Kampli | KT Pura | F8 | 15.03.2022 | IP | 07:00:00AM | 10:00:00PM | 3 Houurs | Scheduled | KT Pura Gouramma kere | Jungle Cuuting
| RSD | 110/11KV MUSS Kampli | Belagodhal | F3 | 24.03.2022 | IP | 10:00:00PM | 02:00:00PM | 4 Houurs | Scheduled | Belagodhal | Jungle Cuuting
| RSD | 110/11KV MUSS Sanklapura | Basavanadurga | F5 | 10.03.2022 | NJY | 11:00:00PM | 01:00:00PM | 2 Hours | Scheduled | Kakubalu, GV Gere, Pk Halli & Vaddarahalli | Jungle Cutting
| RSD | 110/11KV MUSS Sanklapura | P.K.Halli | F7 | 18.03.2022 | IP | 10:30:00PM | 12:30:00PM | 1 Hour | Scheduled | Kakubalu, GV Gere, Kallahalli & Rajapura | DTC Mantainance
| RSD | 110/11KV MUSS Sanklapura | B.V.gere | F7 | 20.03.2022 | IP | 10:00:00AM | 11:00:00AM | 1 Hour | Scheduled | Nagenahalli, Hosuru, Basavanadurga, Benakapura | 11KV GOS Mantanance
| RSD | 110/11KV MUSS Kamalapura | Rajapura | F13 | 25.03.2022 | NJY | 11:30:00AM | 12:30:00PM | 1 Hour | Scheduled | PK Halli, Vadrahalli, BV Gere | Stringing of 11KV Loose Spans
| RSD | 110/11KV MUSS Kamalapura | Hostel | F13 | 27.03.2022 | NJY | 10:00:00AM | 1:00:00PM | 3Hours | Scheduled | PK Halli, Vadrahalli, BV Gere , Gadiganuru, Dharmasagara & Bhuvanahalli | Replacement of Damaged Poles
| RSD | 66/11KV Venkatapura | M.M.Halli | F1 | 15.03.2022 | Urban | 9:00:00AM | 11:00:00AM | 2 Hours | Scheduled | M.M.Halli Town & Nandibandi Pumpset | Jungle Cutting & Insulater Manatanance
| RSD | 66/11KV Venkatapura | Thimmalapura | F9 | 16.03.2022 | NJY | 10:00:00PM | 01:00:00PM | 3 Houurs | Scheduled | Garaga, Nagalapura, Pothalakatte & TB Thanda ETC | Stringing of 11KV Loose Spans
| RSD | 66/11KV Venkatapura | Galemmagudi | F2 | 17.03.2022 | NJY | 10:00:00PM | 01:00:00PM | 3 Houurs | Scheduled | Hanumanahalli, Galemmagudi Danapura | GOS Mantanance & Jungle Cutting
| RSD | 66/11KV Venkatapura | Nagalapura | F8 | 22.03.2022 | IP | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Gunda, Byalakundi, DN Kere & Gollarahalli | Jungle Cutting
| RSD | 66/11KV Venkatapura | Chilakanahatti | F6 | 25.03.2022 | IP | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Haruvanahalli, Chilakanahatti, Thimmalapura & TB Thanda | Jungle Cutting & replacement of Pin Insulater

## April-2022 (hidden)
Tentative Planned Outages for the month of April -2022 of Hospet Urban Division
Name of Division | Name of Subdivision | Name of SubStation | Name of Feeder | Feeder Code | DATE | Feeder Type | Outage From | Outage To | Duration Of Outage | Outage Type | Area Affected | Reason of Outage
Hosapete Urban Division | USD-1 | 33KV MUSS, HOSAPETE | F-5 AMARAVATHI FEEDER | 40020575589 | 05.04.2022 | URBAN | 10:00:00AM | 01:00:00PM | 3 Hours | SCHELDULED | Basaveshwara Badavane, College Road, Chittawadigi, Jabbal Area | Jungle cutting & line GOS maintainance
| USD-1 | 33KV MUSS, HOSAPETE | F-9Chinthamani | 40020575587 | 08.04.2022 | URBAN | 10:00:00AM | 01:00:00PM | 3 Hours | SCHELDULED | Indira Nagar, Rayal orchid Hotel | Line GOS Maintainance
| USD-1 | 33KV MUSS, HOSAPETE | F-10 Patel Nagar | 40020575588 | 13.04.2022 | URBAN | 10:00:00AM | 01:00:00PM | 3 Hours | SCHELDULED | Chapal Gadda, Patel Nagar, Station Road | Line GOS Maintainance
| USD-1 | 110KV Sanklapura | F-9 NC COLONY | 40020575600 | 15.04.2022 | URBAN | 10:00:00AM | 01:00:00PM | 3 Hours | SCHELDULED | Chapparadahalli, Harihara Road, Gandhi Colony, Vivekananda Nagar, Sandur Road, Dam Road | Jungle cutting & line GOS maintainance
| USD-1 | 110KV Sanklapura | F-11 TSP | 40020575598 | 16.04.2022 | URBAN | 10:00:00AM | 01:00:00PM | 3 Hours | SCHELDULED | TB Dam, Gokul Nagar, Sonia Nagar | Jungle cutting & line GOS maintainance
| USD-2 | 110KV MUSS SANKALAPURA | F8-MP.PRAKASH NAGAR | 40020575601 | 04.04.2022 | URBAN | 10:00:00AM | 01:00:00PM | 3 Hours | SCHELDULED | KIADB INDUSTRAIL AREA SANKALAPURA | GOS Alignment MAINTENANCE AND JUNGLE CUTTING Work
| USD-2 | 33KV MUSS | F11 HAMPI ROAD | 40020575584 | 12.04.2022 | URBAN | 10:30:00AM | 02:00:00PM | 2.30 Hours | SCHELDULED | Sankalapura village, sankalapura thanda, bellary road, Ayurvedic college | GOS AligntmentMAINTENANCE
| USD-2 | 110KV MUSS SANKALAPURA | F3- Hospet City | 40020575586 | 21.04.2022 | URBAN | 11:00:00AM | 02:00:00PM | 3 Hours | SCHELDULED | J.N.Halli, J,N,Road | GOS Alignment MAINTENANCE
| RSD | 110/11KV MUSS Kampli | Kampli Town | F2 | 12.04.2022 | Urban | 09:00:00AM | 11:00:00AM | 2 Hours | Scheduled | Main Bazar, Basavanna Temple, Housing Board Colony, Sn Pet Are | Mantanance Work
| RSD | 110/11KV MUSS Kampli | Kampli Kottal | F4 | 17.04.2022 | Urban | 10:00:00AM | 12:00:00PM | 2 Hours | Scheduled | Vinayaka Nagara, Idira Nagara, Sanapura Road, Kottal Road | DTC Wiring
| RSD | 110/11KV MUSS Kampli | Industrial | F3 | 20.04.2022 | Urban | 09:00:00AM | 01:00:00PM | 4 Hours | Scheduled | Kottal | GOS Mantanance
| RSD | 110/11KV MUSS Kampli | Basaveshwara Nagara | F12 | 22.04.2022 | Urban | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Basaveshwara Nagara, Maruthi Nagara | Line Mantanance
| RSD | 110/11KV MUSS Kampli | Prabhu Camp | F13 | 28.04.2022 | Urban | 10:00:00AM | 12:00:00PM | 2 Hours | Scheduled | Sugar Factory, Prabhu Camp, Huligemma Camp | Line Mantanance
| RSD | 110/11KV MUSS Kamalapura | Kamalapura Town | F12 | 10.04.2022 | Urban | 09:00:00AM | 12:00:00PM | 3 Hours | Scheduled | Kamalapura Town | Jungle Cutting
| RSD | 110/11KV MUSS Kamalapura | Nallapura | F3 | 15.04.2022 | NJY | 09:00:00AM | 12:00:00PM | 3 Hours | Scheduled | Nallapura, Hosa Chinnapura SR Thanda | GOS Mantanance
| RSD | 110/11KV MUSS Kamalapura | Malapanagudi | F2 | 21.04.2022 | Rural | 11:00:00AM | 06:00:00PM | 7 Hours | Scheduled | Hosa Malapanagudi, galemmagudi | Stringing of 11KV Loose Spans
| RSD | 110/11KV MUSS Kamalapura | University | F4 | 17.04.2022 | Rural | 12:00:00AM | 02:00:00PM | 2 Hours | Scheduled | University, Nallapura | GOS Mantanance & Jungle Cutting
| RSD | 110/11KV MUSS Kampli | Vidyapeeta | F6 | 12.04.2022 | NJY | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Ramasagara, Kanavi Thimmalapura | Jungle Cuuting
| RSD | 110/11KV MUSS Kampli | KT Pura | F8 | 10.04.2022 | IP | 07:00:00AM | 10:00:00PM | 3 Hours | Scheduled | KT Pura Gouramma kere | Jungle Cuuting
| RSD | 110/11KV MUSS Kampli | Belagodhal | F3 | 23.04.2022 | IP | 10:00:00PM | 02:00:00PM | 4 Hours | Scheduled | Belagodhal | Jungle Cuuting
| RSD | 110/11KV MUSS Sanklapura | Basavanadurga | F5 | 08.04.2022 | NJY | 11:00:00PM | 01:00:00PM | 2 Hours | Scheduled | Kakubalu, GV Gere, Pk Halli & Vaddarahalli | Jungle Cutting
| RSD | 110/11KV MUSS Sanklapura | P.K.Halli | F7 | 11.04.2022 | IP | 10:30:00PM | 12:30:00PM | 1 Hour | Scheduled | Kakubalu, GV Gere, Kallahalli & Rajapura | DTC Mantainance
| RSD | 110/11KV MUSS Sanklapura | B.V.gere | F7 | 19.04.2022 | IP | 10:00:00AM | 11:00:00AM | 1 Hour | Scheduled | Nagenahalli, Hosuru, Basavanadurga, Benakapura | 11KV GOS Mantanance
| RSD | 110/11KV MUSS Kamalapura | Rajapura | F13 | 24.04.2022 | NJY | 11:30:00AM | 12:30:00PM | 1 Hour | Scheduled | PK Halli, Vadrahalli, BV Gere | Stringing of 11KV Loose Spans
| RSD | 110/11KV MUSS Kamalapura | Hostel | F13 | 26.04.2022 | NJY | 10:00:00AM | 1:00:00PM | 3 Hours | Scheduled | PK Halli, Vadrahalli, BV Gere , Gadiganuru, Dharmasagara & Bhuvanahalli | Replacement of Damaged Poles
| RSD | 66/11KV Venkatapura | M.M.Halli | F1 | 14.04.2022 | Urban | 9:00:00AM | 11:00:00AM | 2 Hours | Scheduled | M.M.Halli Town & Nandibandi Pumpset | Jungle Cutting & Insulater Manatanance
| RSD | 66/11KV Venkatapura | Thimmalapura | F9 | 18.04.2022 | NJY | 10:00:00PM | 01:00:00PM | 3 Hours | Scheduled | Garaga, Nagalapura, Pothalakatte & TB Thanda ETC | Stringing of 11KV Loose Spans
| RSD | 66/11KV Venkatapura | Galemmagudi | F2 | 20.04.2022 | NJY | 10:00:00PM | 01:00:00PM | 3 Hours | Scheduled | Hanumanahalli, Galemmagudi Danapura | GOS Mantanance & Jungle Cutting
| RSD | 66/11KV Venkatapura | Nagalapura | F8 | 19.04.2022 | IP | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Gunda, Byalakundi, DN Kere & Gollarahalli | Jungle Cutting
| RSD | 66/11KV Venkatapura | Chilakanahatti | F6 | 25.04.2022 | IP | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Haruvanahalli, Chilakanahatti, Thimmalapura & TB Thanda | Jungle Cutting & replacement of Pin Insulater

## May-2022 (hidden)
Tentative Planned Outages for the month of May -2022 of Hospet Urban Division
Name of Division | Name of Subdivision | Name of SubStation | Name of Feeder | Feeder Code | DATE | Feeder Type | Outage From | Outage To | Duration Of Outage | Outage Type | Area Affected | Reason of Outage
Hosapete Urban Division | USD-1 | 33KV MUSS, HOSAPETE | F-5 AMARAVATHI FEEDER | 40020575589 | 06.05.2022 | URBAN | 10:00:00AM | 01:00:00PM | 3 Hours | SCHELDULED | Basaveshwara Badavane, College Road, Chittawadigi, Jabbal Area | Jungle cutting & line GOS maintainance
| USD-1 | 33KV MUSS, HOSAPETE | F-9Chinthamani | 40020575587 | 11.05.2022 | URBAN | 10:00:00AM | 01:00:00PM | 3 Hours | SCHELDULED | Indira Nagar, Rayal orchid Hotel | Line GOS Maintainance
| USD-1 | 33KV MUSS, HOSAPETE | F-10 Patel Nagar | 40020575588 | 13.05.2022 | URBAN | 10:00:00AM | 01:00:00PM | 3 Hours | SCHELDULED | Chapal Gadda, Patel Nagar, Station Road | Line GOS Maintainance
| USD-1 | 110KV Sanklapura | F-9 NC COLONY | 40020575600 | 18.05.2022 | URBAN | 10:00:00AM | 01:00:00PM | 3 Hours | SCHELDULED | Chapparadahalli, Harihara Road, Gandhi Colony, Vivekananda Nagar, Sandur Road, Dam Road | Jungle cutting & line GOS maintainance
| USD-1 | 110KV Sanklapura | F-11 TSP | 40020575598 | 20.05.2022 | URBAN | 10:00:00AM | 01:00:00PM | 3 Hours | SCHELDULED | TB Dam, Gokul Nagar, Sonia Nagar | Jungle cutting & line GOS maintainance
| USD-2 | 110KV MUSS SANKALAPURA | F8-MP.PRAKASH NAGAR | 40020575601 | 11.05.2022 | URBAN | 10:00:00AM | 01:00:00PM | 3 Hours | SCHELDULED | KIADB INDUSTRAIL AREA SANKALAPURA | GOS Alignment MAINTENANCE AND JUNGLE CUTTING Work
| USD-2 | 33KV MUSS | F11 HAMPI ROAD | 40020575584 | 15.05.2022 | URBAN | 10:30:00AM | 02:00:00PM | 2.30 Hours | SCHELDULED | Sankalapura village, sankalapura thanda, bellary road, Ayurvedic college | GOS AligntmentMAINTENANCE
| USD-2 | 110KV MUSS SANKALAPURA | F3- Hospet City | 40020575586 | 19.05.2022 | URBAN | 11:00:00AM | 02:00:00PM | 3 Hours | SCHELDULED | J.N.Halli, J,N,Road | GOS Alignment MAINTENANCE
| RSD | 110/11KV MUSS Kampli | Kampli Town | F2 | 11.05.2022 | Urban | 09:00:00AM | 11:00:00AM | 2 Hours | Scheduled | Main Bazar, Basavanna Temple, Housing Board Colony, Sn Pet Are | Mantanance Work
| RSD | 110/11KV MUSS Kampli | Kampli Kottal | F4 | 15.05.2022 | Urban | 10:00:00AM | 12:00:00PM | 2 Hours | Scheduled | Vinayaka Nagara, Idira Nagara, Sanapura Road, Kottal Road | DTC Wiring
| RSD | 110/11KV MUSS Kampli | Industrial | F3 | 19.05.2022 | Urban | 09:00:00AM | 01:00:00PM | 4 Hours | Scheduled | Kottal | GOS Mantanance
| RSD | 110/11KV MUSS Kampli | Basaveshwara Nagara | F12 | 21.05.2022 | Urban | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Basaveshwara Nagara, Maruthi Nagara | Line Mantanance
| RSD | 110/11KV MUSS Kampli | Prabhu Camp | F13 | 23.05.2022 | Urban | 10:00:00AM | 12:00:00PM | 2 Hours | Scheduled | Sugar Factory, Prabhu Camp, Huligemma Camp | Line Mantanance
| RSD | 110/11KV MUSS Kamalapura | Kamalapura Town | F12 | 12.05.2022 | Urban | 09:00:00AM | 12:00:00PM | 3 Hours | Scheduled | Kamalapura Town | Jungle Cutting
| RSD | 110/11KV MUSS Kamalapura | Nallapura | F3 | 14.05.2022 | NJY | 09:00:00AM | 12:00:00PM | 3 Hours | Scheduled | Nallapura, Hosa Chinnapura SR Thanda | GOS Mantanance
| RSD | 110/11KV MUSS Kamalapura | Malapanagudi | F2 | 22.05.2022 | Rural | 11:00:00AM | 06:00:00PM | 7 Hours | Scheduled | Hosa Malapanagudi, galemmagudi | Stringing of 11KV Loose Spans
| RSD | 110/11KV MUSS Kamalapura | University | F4 | 18.05.2022 | Rural | 12:00:00AM | 02:00:00PM | 2 Hours | Scheduled | University, Nallapura | GOS Mantanance & Jungle Cutting
| RSD | 110/11KV MUSS Kampli | Vidyapeeta | F6 | 17.05.2022 | NJY | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Ramasagara, Kanavi Thimmalapura | Jungle Cuuting
| RSD | 110/11KV MUSS Kampli | KT Pura | F8 | 13.05.2022 | IP | 07:00:00AM | 10:00:00PM | 3 Hours | Scheduled | KT Pura Gouramma kere | Jungle Cuuting
| RSD | 110/11KV MUSS Kampli | Belagodhal | F3 | 22.05.2022 | IP | 10:00:00PM | 02:00:00PM | 4 Hours | Scheduled | Belagodhal | Jungle Cuuting
| RSD | 110/11KV MUSS Sanklapura | Basavanadurga | F5 | 10.05.2022 | NJY | 11:00:00PM | 01:00:00PM | 2 Hours | Scheduled | Kakubalu, GV Gere, Pk Halli & Vaddarahalli | Jungle Cutting
| RSD | 110/11KV MUSS Sanklapura | P.K.Halli | F7 | 15.05.2022 | IP | 10:30:00PM | 12:30:00PM | 1 Hour | Scheduled | Kakubalu, GV Gere, Kallahalli & Rajapura | DTC Mantainance
| RSD | 110/11KV MUSS Sanklapura | B.V.gere | F7 | 17.05.2022 | IP | 10:00:00AM | 11:00:00AM | 1 Hour | Scheduled | Nagenahalli, Hosuru, Basavanadurga, Benakapura | 11KV GOS Mantanance
| RSD | 110/11KV MUSS Kamalapura | Rajapura | F13 | 21.05.2022 | NJY | 11:30:00AM | 12:30:00PM | 1 Hour | Scheduled | PK Halli, Vadrahalli, BV Gere | Stringing of 11KV Loose Spans
| RSD | 110/11KV MUSS Kamalapura | Hostel | F13 | 25.05.2022 | NJY | 10:00:00AM | 1:00:00PM | 3 Hours | Scheduled | PK Halli, Vadrahalli, BV Gere , Gadiganuru, Dharmasagara & Bhuvanahalli | Replacement of Damaged Poles
| RSD | 66/11KV Venkatapura | M.M.Halli | F1 | 12.05.2022 | Urban | 9:00:00AM | 11:00:00AM | 2 Hours | Scheduled | M.M.Halli Town & Nandibandi Pumpset | Jungle Cutting & Insulater Manatanance
| RSD | 66/11KV Venkatapura | Thimmalapura | F9 | 16.05.2022 | NJY | 10:00:00PM | 01:00:00PM | 3 Hours | Scheduled | Garaga, Nagalapura, Pothalakatte & TB Thanda ETC | Stringing of 11KV Loose Spans
| RSD | 66/11KV Venkatapura | Galemmagudi | F2 | 20.05.2022 | NJY | 10:00:00PM | 01:00:00PM | 3 Hours | Scheduled | Hanumanahalli, Galemmagudi Danapura | GOS Mantanance & Jungle Cutting
| RSD | 66/11KV Venkatapura | Nagalapura | F8 | 17.05.2022 | IP | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Gunda, Byalakundi, DN Kere & Gollarahalli | Jungle Cutting
| RSD | 66/11KV Venkatapura | Chilakanahatti | F6 | 23.05.2022 | IP | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Haruvanahalli, Chilakanahatti, Thimmalapura & TB Thanda | Jungle Cutting & replacement of Pin Insulater

## March
Tentative Planned Outages for the month of Mar -2023 of Hospet Urban Division
Name of Division | Name of Subdivision | Name of SubStation | Name of Feeder | Feeder Code | DATE | Feeder Type | Outage From | Outage To | Duration Of Outage | Outage Type | Area Affected | Reason of Outage
Hosapete Urban Division | USD-1 | 33KV MUSS, HOSAPETE | F-5 AMARAVATHI FEEDER | 40020575589 | 2023-04-03 | URBAN | 10:00:00AM | 01:00:00PM | 3 Hours | Scheduled | Industrial area, Rajeev Nagar, Chittawadigi, Amaravathi, Sai Ram Badavane, Kalyan Nagar, Mallinath Layout | Line GOS Maintainance
| USD-1 | 33KV MUSS, HOSAPETE | STATION ROAD | 40020575589 | 2023-06-03 | URBAN | 10:00:00AM | 01:00:00PM | 3 Hours | Scheduled | basaveshwara badavane varakeri, | Line GOS Maintainance
| USD-1 | 33KV MUSS, HOSAPETE | F-10 Patel Nagar | 40020575588 | 2023-04-03 | URBAN | 10:00:00AM | 01:00:00PM | 3 Hours | Scheduled | Chapal Gadda, Patel Nagar, Station Road | Line GOS Maintainance
| USD-1 | 110KV Sanklapura | F-9 NC COLONY | 40020575600 | 2023-06-03 | URBAN | 10:00:00AM | 01:00:00PM | 3 Hours | Scheduled | Chapparadahalli, Harihara Road, Gandhi Colony, Vivekananda Nagar, Sandur Road, Dam Road | Jungle cutting & line GOS maintainance
| USD-1 | 110KV Sanklapura | F-11 TSP | 40020575598 | 2023-04-03 | URBAN | 10:00:00AM | 01:00:00PM | 3 Hours | Scheduled | TB Dam, Gokul Nagar, Sonia Nagar | Jungle cutting & line GOS maintainance
| USD-2 | 110KV MUSS SANKALAPURA | F1-Rama Feeder | 40020575594 | 2023-03-06 | URBAN | 10:00:00AM | 02:00:00PM | 4 Hours | SCHELDULED | PARVATHI NAGAR, AKASHVANI, N.C.COLONY, MYASAKERI, TALVALKERI, CHITTARKERI, OLD VEGTABLE MARKET, COWL PETE, S.R.NAGAR, CHALUVADIKERI, A C OFFICE | GOS AligntmentMAINTENANCE
| USD-2 | 33KV MUSS | F11 HAMPI ROAD | 40020575584 | 17.03.2023 | URBAN | 10:00:00AM | 01:00:00PM | 3 Hours | SCHELDULED | SUNNADA BHAATTI , JAIN COLONY , HAMPI ROAD, | GOS MAINTENANCE
| USD-2 | 110KV MUSS SANKALAPURA | F4-KOF | 40020575591 | 2023-03-21 | URBAN | 10:00:00AM | 01:00:00PM | 3 Hours | SCHELDULED | KIADB INDUSTRAIL AREA SANKALAPURA | GOS Alignment MAINTENANCE AND JUNGLE CUTTING Work
| RSD | 110/11KV MUSS Kampli | Kampli Town | F2 | 01.03.2023 | Urban | 09:00:00AM | 11:00:00AM | 2 Hours | Scheduled | Main Bazar, Basavanna Temple, Housing Board Colony, Sn Pet Are | Mantanance Work
| RSD | 110/11KV MUSS Kampli | Kampli Kottal | F4 | 09.03.2023 | Urban | 10:00:00AM | 12:00:00PM | 2 Hours | Scheduled | Vinayaka Nagara, Idira Nagara, Sanapura Road, Kottal Road | DTC Wiring
| RSD | 110/11KV MUSS Kampli | Industrial | F3 | 12.03.2023 | Urban | 09:00:00AM | 01:00:00PM | 4Hours | Scheduled | Kottal | GOS Mantanance
| RSD | 110/11KV MUSS Kampli | Basaveshwara Nagara | F12 | 15.03.2023 | Urban | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Basaveshwara Nagara, Maruthi Nagara | Line Mantanance
| RSD | 110/11KV MUSS Kampli | Prabhu Camp | F13 | 18.03.2023 | Urban | 10:00:00AM | 12:00:00PM | 2 Hours | Scheduled | Sugar Factory, Prabhu Camp, Huligemma Camp | Line Mantanance
| RSD | 110/11KV MUSS Kamalapura | Kamalapura Town | F12 | 2.03.2023 | Urban | 09:00:00AM | 12:00:00PM | 3 Hours | Scheduled | Kamalapura Town | Jungle Cutting
| RSD | 110/11KV MUSS Kamalapura | Nallapura | F3 | 4.03.2023 | NJY | 09:00:00AM | 12:00:00PM | 3 Hours | Scheduled | Nallapura, Hosa Chinnapura SR Thanda | GOS Mantanance
| RSD | 110/11KV MUSS Kamalapura | Malapanagudi | F2 | 12.03.2023 | Rural | 11:00:00AM | 06:00:00PM | 7 Hours | Scheduled | Hosa Malapanagudi, galemmagudi | Stringing of 11KV Loose Spans
| RSD | 110/11KV MUSS Kamalapura | University | F4 | 22.03.2023 | Rural | 12:00:00AM | 02:00:00PM | 2 Hours | Scheduled | University, Nallapura | GOS Mantanance & Jungle Cutting
| RSD | 110/11KV MUSS Kamalapura | Hostel | F13 | 15.03.2023 | NJY | 10:00:00AM | 1:00:00PM | 3Hours | Scheduled | PK Halli, Vadrahalli, BV Gere , Gadiganuru, Dharmasagara & Bhuvanahalli | Replacement of Damaged Poles
| RSD | 110/11KV MUSS Kampli | Vidyapeeta | F6 | 17.03.2023 | NJY | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Ramasagara, Kanavi Thimmalapura | Jungle Cuuting
| RSD | 110/11KV MUSS Kampli | KT Pura | F8 | 22.03.2023 | IP | 07:00:00AM | 10:00:00PM | 3 Hours | Scheduled | KT Pura Gouramma kere | Jungle Cuuting
| RSD | 110/11KV MUSS Kampli | Belagodhal | F3 | 25.03.2023 | IP | 10:00:00PM | 02:00:00PM | 4 Hours | Scheduled | Belagodhal | Jungle Cuuting
| RSD | 110/11KV MUSS Sanklapura | Basavanadurga | F5 | 01.03.2023 | NJY | 11:00:00PM | 01:00:00PM | 2 Hours | Scheduled | Kakubalu, GV Gere, Pk Halli & Vaddarahalli | Jungle Cutting
| RSD | 110/11KV MUSS Sanklapura | P.K.Halli | F7 | 14.03.2023 | IP | 10:30:00PM | 12:30:00PM | 1 Hour | Scheduled | Kakubalu, GV Gere, Kallahalli & Rajapura | DTC Mantainance
| RSD | 110/11KV MUSS Sanklapura | B.V.gere | F7 | 28.03.2023 | IP | 10:00:00AM | 11:00:00AM | 1 Hour | Scheduled | Nagenahalli, Hosuru, Basavanadurga, Benakapura | 11KV GOS Mantanance
| RSD | 110/11KV MUSS Sanklapura | Rajapura | F13 | 29.03.2023 | NJY | 11:30:00AM | 12:30:00PM | 1 Hour | Scheduled | PK Halli, Vadrahalli, BV Gere | Stringing of 11KV Loose Spans
| RSD | 66/11KV Venkatapura | M.M.Halli | F1 | 05.03.2023 | Urban | 9:00:00AM | 11:00:00AM | 2 Hours | Scheduled | M.M.Halli Town & Nandibandi Pumpset | Jungle Cutting & Insulater Manatanance
| RSD | 66/11KV Venkatapura | Thimmalapura | F9 | 09.03.2023 | NJY | 10:00:00PM | 01:00:00PM | 3 Hours | Scheduled | Garaga, Nagalapura, Pothalakatte & TB Thanda ETC | Stringing of 11KV Loose Spans
| RSD | 66/11KV Venkatapura | Galemmagudi | F2 | 25.03.2023 | NJY | 10:00:00PM | 01:00:00PM | 3 Hours | Scheduled | Hanumanahalli, Galemmagudi Danapura | GOS Mantanance & Jungle Cutting
| RSD | 66/11KV Venkatapura | Nagalapura | F8 | 26.03.2023 | IP | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Gunda, Byalakundi, DN Kere & Gollarahalli | Jungle Cutting
| RSD | 66/11KV Venkatapura | Chilakanahatti | F6 | 29.03.2023 | IP | 11:00:00AM | 01:00:00PM | 2 Hours | Scheduled | Haruvanahalli, Chilakanahatti, Thimmalapura & TB Thanda | Jungle Cutting & replacement of Pin Insulater