## August-2021
Tentative Planned Outages for the month of August-2021 of Hospet Urban
Name of Division | Name of Subdivision | Name of SubStation | Name of Feeder | Feeder Code | Feeder Type | Date | Outage From | Outage To | Duration Of Outage | Outage Type | Area Affected | Reason of Outage
Hosapete Urban | USD-1 | 33KV MUSS, HOSAPETE | F-5 AMARAVATHI FEEDER | 40020575589 | URBAN | 2021-08-11 | 10:00:00AM | 01:00:00PM | 3.00 HRS | SCHELDULED | Industrial area, Rajeev Nagar, Chittawadigi, Amaravathi, Sai Ram Badavane, Kalyan Nagar, Mallinath Layout | Jungle cutting & line GOS maintainance
| USD-1 | 33KV MUSS, HOSAPETE | F-4 Ennoble | 40020575583 | URBAN | 2021-08-12 | 10:00:00AM | 01:00:00PM | 3.00 HRS | SCHELDULED | Indira Nagar, Rayal orchid Hotel | Line GOS Maintainance
| USD-2 | 110KV MUSS SANKALAPURA | F8-MP.PRAKASH NAGAR | 40020575601 | URBAN | 10.08.2021 | 10:00:00AM | 01:00:00PM | 3.00 HRS | SCHELDULED | MP.PRAKASH NAGAR, SANKALAPURA, A.S.GUDI, SAI COLONY, KN.HALLI | GOS MAINTENANCE
| RSD | 110/11KV MUSS Sanklapura | BV Gere | F7 | IP | 14.08.2021 | 09:00:00AM | 01:00:00PM | 4Hours | SCHELDULED | Kakubalu, GV Gere, Pk Halli & Vaddarahalli | Jungle Cutting
| RSD | 110/11KV MUSS Sanklapura | Rajapura | F13 | NJY | 16.08.2021 | 11:00:00AM | 01:00:00PM | 2 Hours | SCHELDULED | Kakubalu, GV Gere, Kallahalli & Rajapura | DTC Mantainance
| RSD | 110/11KV MUSS Sanklapura | Basavanadurga | F5 | NJY | 18.08.2021 | 10:00:00AM | 12:00:00PM | 2 Hours | SCHELDULED | Nagenahalli, Hosuru, Basavanadurga, Benakapura | 11KV GOS Mantanance
| RSD | 110/11KV MUSS Kamalapura | P.K.Halli | F7 | IP | 20.08.2021 | 09:00:00AM | 12:00:00PM | 3 Hours | SCHELDULED | PK Halli, Vadrahalli, BV Gere | Stringing of 11KV Loose Spans
| RSD | 110/11KV MUSS Kamalapura | Hostel | F13 | NJY | 22.08.2021 | 09:00:00AM | 12:00:00PM | 3 Hours | SCHELDULED | PK Halli, Vadrahalli, BV Gere , Gadiganuru, Dharmasagara & Bhuvanahalli | Replacement of Damaged Poles
| RSD | 66/11KV Venkatapura | M.M.Halli | F1 | Urban | 18.08.2021 | 11:00:00AM | 06:00:00PM | 7 Hours | SCHELDULED | M.M.Halli Town & Nandibandi Pumpset | Jungle Cutting & Insulater Manatanance
| RSD | 66/11KV Venkatapura | Thimmalapura | F9 | NJY | 20.08.2021 | 12:00:00AM | 02:00:00PM | 2 Hours | SCHELDULED | Garaga, Nagalapura, Pothalakatte & TB Thanda ETC | Stringing of 11KV Loose Spans
| RSD | 66/11KV Venkatapura | Galemmagudi | F2 | NJY | 22.08.2021 | 11:00:00AM | 01:00:00PM | 2 Hours | SCHELDULED | Hanumanahalli, Galemmagudi Danapura | GOS Mantanance & Jungle Cutting
| RSD | 66/11KV Venkatapura | Nagalapura | F8 | IP | 24.08.2021 | 07:00:00AM | 10:00:00PM | 3 Houurs | SCHELDULED | Gunda, Byalakundi, DN Kere & Gollarahalli | Jungle Cutting
| RSD | 66/11KV Venkatapura | Chilakanahatti | F6 | IP | 26.08.2021 | 10:00:00PM | 02:00:00PM | 4 Houurs | SCHELDULED | Haruvanahalli, Chilakanahatti, Thimmalapura & TB Thanda | Jungle Cutting & replacement of Pin Insulater
| RSD | 110/11KV MUSS Kampli | Kampli Town | F2 | Urban | 14.08.2021 | 11:00:00PM | 01:00:00PM | 2 Hours | SCHELDULED | Main Bazar, Basavanna Temple, Housing Board Colony, Sn Pet Are | Mantanance Work
| RSD | 110/11KV MUSS Kampli | Kampli Kottal | F4 | Urban | 16.08.2021 | 10:30:00PM | 12:30:00PM | 1 Hour | SCHELDULED | Vinayaka Nagara, Idira Nagara, Sanapura Road, Kottal Road | DTC Wiring
| RSD | 110/11KV MUSS Kampli | Industrial | F3 | Urban | 18.08.2021 | 10:00:00AM | 11:00:00AM | 1 Hour | SCHELDULED | Kottal | GOS Mantanance
| RSD | 110/11KV MUSS Kampli | Basaveshwara Nagara | F12 | Urban | 19.08.2021 | 11:30:00AM | 12:30:00PM | 1 Hour | SCHELDULED | Basaveshwara Nagara, Maruthi Nagara | Line Mantanance
| RSD | 110/11KV MUSS Kampli | Prabhu Camp | F13 | Urban | 20.08.2021 | 10:00:00AM | 1:00:00PM | 3Hours | SCHELDULED | Sugar Factory, Prabhu Camp, Huligemma Camp | Line Mantanance
| RSD | 110/11KV MUSS Kamalapura | Kamalapura Town | F12 | Urban | 14.08.2021 | 9:00:00AM | 11:00:00AM | 2 Hours | SCHELDULED | Kamalapura Town | Jungle Cutting
| RSD | 110/11KV MUSS Kamalapura | Nallapura | F3 | NJY | 16.08.2021 | 10:00:00PM | 01:00:00PM | 3 Houurs | SCHELDULED | Nallapura, Hosa Chinnapura SR Thanda | GOS Mantanance
| RSD | 110/11KV MUSS Kamalapura | Malapanagudi | F2 | Rural | 18.08.2021 | 10:00:00PM | 01:00:00PM | 3 Houurs | SCHELDULED | Hosa Malapanagudi, galemmagudi | Stringing of 11KV Loose Spans
| RSD | 110/11KV MUSS Kamalapura | University | F4 | Rural | 20.08.2021 | 11:00:00AM | 01:00:00PM | 2 Hours | SCHELDULED | University, Nallapura | GOS Mantanance & Jungle Cutting
| RSD | 110/11KV MUSS Kampli | Vidyapeeta | F6 | NJY | 9.08.2021 | 11:00:00AM | 01:00:00PM | 2 Hours | SCHELDULED | Ramasagara, Kanavi Thimmalapura | Jungle Cuuting
| RSD | 110/11KV MUSS Kampli | KT Pura | F8 | IP | 12.08.2021 | 09:00:00AM | 11:00:00AM | 2 Hours | SCHELDULED | KT Pura Gouramma kere | Jungle Cuuting
| RSD | 110/11KV MUSS Kampli | Belagodhal | F3 | IP | 19.08.2021 | 10:00:00AM | 12:00:00PM | 2 Hours | SCHELDULED | Belagodhal | Jungle Cuuting