## edited
Status of GPS Survey of IP Sets as on 31-12-2021
Name of the Company
Name of the ESCOM: GESCOM
Date of commencement of GPS Survey: DWA NO:- 46771-852 dated:29-12-2016.
Date of completion of GPS Survey: Under process
If incomplete, Probable date of completion: Survey completed, details to be updated in data base.
Sl No | Division | Total Number of 11kV Feeders Existing (NJY +IP+Rural) | No of Rural Feeder Existing | No of Agricultural Feeder Existing (IP) | No of Feeders for which GPS Survey is completed | No of IP installations, LT4 category existing as on Dec-2021, as per DCB | No of IP DTCs Surveyed | No of IP installations, Surveyed as on 31-12-2021 | % of GPS Survey completed | Data as per GPS survey as on 31-12-2021(Authorised IP sets) |  |  | Data as per GPS survey as on 31-12-2021 (Unauthorised IP sets)
[10 empty] | No of IP sets surveyed | No of IP sets defunct/dried up/disconnected | Total No of live / working IP sets, LT4 | No of IP sets surveyed | No of IP sets defunct/dried up/disconnected | Total No of live / working IP sets, LT4
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10=9*100/7 | 11=12+13 | 12 | 13 | 14=15+16 | 15 | 16
1 | BIDAR | 153 | 2 | 85 | 139 | 43053 | 5535 | 39767 | 92.3675 | 39237 | 1915 | 37322 | 530 | 128 | 402
2 | HUMNABAD | 108 | 1 | 67 | 93 | 40570 | 3654 | 36406 | 89.7363 | 36125 | 784 | 35341 | 281 | 69 | 212
3 | KALABURAGI-I | 178 | 0 | 105 | 116 | 53304 | 5558 | 51982 | 97.5199 | 48274 | 1848 | 46426 | 3708 | 917 | 2791
4 | KALABURAGI-II | 89 | 0 | 44 | 76 | 17480 | 2581 | 14106 | 80.6979 | 12658 | 168 | 12490 | 1448 | 94 | 1354
5 | SEDAM | 78 | 3 | 31 | 64 | 11241 | 1606 | 10178 | 90.5435 | 9836 | 272 | 9564 | 342 | 85 | 257
6 | YADGIR | 155 | 7 | 86 | 142 | 37008 | 4626 | 32370 | 87.4676 | 31442 | 275 | 31167 | 928 | 116 | 812
7 | GANGAVATHI | 116 | 6 | 81 | 88 | 29526 | 4776 | 35576 | 120.4904 | 27945 | 1847 | 26098 | 7631 | 1231 | 6400
8 | HOSPET | 183 | 0 | 128 | 230 | 52555 | 11471 | 61252 | 116.5484 | 51195 | 2698 | 48497 | 10057 | 1952 | 8105
9 | KOPPAL | 125 | 0 | 90 | 132 | 35762 | 5996 | 37599 | 105.1367 | 33885 | 371 | 33514 | 3714 | 145 | 3569
10 | RAICHUR | 186 | 0 | 105 | 185 | 32383 | 6478 | 36202 | 111.7932 | 30604 | 554 | 30050 | 5598 | 232 | 5366
11 | SINDHANOOR | 138 | 2 | 78 | 91 | 25905 | 4232 | 26938 | 103.9876 | 23004 | 134 | 22870 | 3934 | 97 | 3837
12 | BALLARI | 121 | 0 | 80 | 101 | 37430 | 6155 | 37235 | 99.479 | 30335 | 512 | 29823 | 6900 | 734 | 6166
Total |  | 1630 | 21 | 980 | 1457 | 416224 | 62668 | 419611 | 100.8137 | 374540 | 11378 | 363162 | 45071 | 5800 | 39271
The mismatch of IP sets (Unauthorized)count is 45071 in order to regularize the Unauthorized IP sets existing in the field, division wise breakup of No. of IP sets (Unauthorized) sent to divisional officers to carry out Physical inventory in the field and furnish the actual status of Unauthorized ipsets.
|  | Total Number of 11kV Feeders Existing | No of Rural Feeder Existing | No of Agricultural Feeder Existing
Updated from SCADA as on 30-11-2022